## H & F.W._NP(M)
Statement showing Allotment of funds for Building works of H & FW Department (NP) 2010-11
Date :- 9-7-2010
Sl. No. | Head of Account / Name of the Work | OBP of 2010-11 | A.A. Cost with No. & Date |  |  | Name of Division | Funds alloted upto 3/2010 (inclusive PC 20%) | Funds alloted 2010-11 (inclusive PC 20%) | Expenditure | Physical Progress
1 | 2 | 3 | 4 |  |  | 5 | 6 | 7 | 8 | 9
D. No-7-2210-M&PH-01-UHS-Allopathy-110 -H&D-2054- Improvement of buildings.
1 | Improvement of land scape & provisons for 3 Govt. Allopathic Medical Colleges @ Rs. 100.00 laksh each VSS MCH, Burla | 25 | DMET No.15329 / 17.11.08 | C.W. | 100 | Baragarh | 75 | 25
|  |  |  | Total = | 100 |  | 75 | 25
2 | Improvement of Nursing School in V.S.S. Medical Colleges, Burla. | 23 | DMET No.20038 / 22.12.07 | C.W. | 30 | Baragarh | 10 | 20
|  |  |  | E.I. | 3 | GED-III |  | 3
|  |  |  | P.H. |  | GPH-II
|  |  |  | Total = | 33 |  | 10 | 23
|  | 48 |  |  | 133 |  | 85 | 48
3 | Improvement of land scape & provisons for 3 Govt. Allopathic Medical Colleges @ Rs. 100.00 laksh each MKCG MCH, Berhampur. | 0.59 | DMET No.13673 / 04.10.08 | C.W. | 98.65 | Ganjam-I | 98.65
|  |  |  | E.I. | 0.76 | GED-I | 0.76
|  |  |  | P.H. | 0.59 | GPH-I |  | 0.59
|  |  |  | Total = | 100 |  | 99.41 | 0.59
4 | Improvement of Nursing School in M.K.C.G. MCH, Berhampur. | 4.2 | DMET No.19180 / 12.12.07 | C.W. | 27 | Ganjam-I | 27
|  |  |  | E.I. | 1.8 | GED-I | 1.8
|  |  |  | P.H. | 4.2 | GPH-I |  | 4.2
|  |  |  | Total = | 33 |  | 28.8 | 4.2
5 | Hostel facilities for Nursing College, M.K.C.G. MCH, Berhampur. | 4.35 | DMET No.19190 / 12.12.07 | C.W. | 33.4 | Ganjam-I | 33.4
|  |  |  | E.I. | 2.25 | GED-I | 2.25
|  |  |  | P.H. | 4.35 | GPH-I |  | 4.35
|  |  |  | Total = | 40 |  | 35.65 | 4.35
6 | Accommodation for Staff Nurses in M.K.C.G. MCH, Berhampur. | 3.41 | DMET No.20329 / 28.12.07 | C.W. | 23.06 | Ganjam-I | 23.06
|  |  |  | E.I. | 1.98 | GED-I | 1.98
|  |  |  | P.H. (I) | 1.98 | GPH-I | 1.55 | 3.41
|  |  |  | P.H.(E) | 2.98
|  |  |  | Total = | 30 |  | 26.59 | 3.41
|  | 12.55 |  |  | 203 |  | 190.45 | 12.55
7 | Constn. of 2nos. Gates including footpath, median and short approaches within the SCB MCH premises. | 75 |  | C.W. |  | Cuttack |  | 75
|  |  |  | Total = | 0 |  | 0 | 75
8 | Accommodation for Staff Nurses in SCB, MCH, Cuttack | 10 |  | C.W. | 70 | Cuttack | 60 | 10
|  |  |  | Total = | 70 |  | 60 | 10
9 | Renovation of medicine Dept. and ward O & G Dept. and ward, Surgery Dept. and ward of SCB MCH, Cuttack. | 59.08 | H & FW No.20130 / 30.08.08 | C.W. | 266.4 | Cuttack | 200 | 59.08
|  |  |  | E.I. | 16.8 | GED-I | 23.02
|  |  |  | P.H. | 16.8 | GPH-I | 17.08
|  |  |  | Total = | 300 |  | 240.1 | 59.08
|  | 144.08 |  |  | 370 |  | 300.1 | 144.08
10 | Impvt. of building of Govt. Ayurvedic College, Bolangir | 28.07 | DIMH (O) No.10179 / 28.08.08 | C.W. | 49.56 | Bolangir | 24.58 | 24.98
|  |  |  | E.I. | 4.09 | GED-III | 1 | 3.09
|  |  |  | P.H. | 6.33 | GPH-II | 6.33
|  |  |  | Total = | 59.98 |  | 31.91 | 28.07
11 | Improvement of DHH at Sonepur. | 10 | DHS (O) No.9556 / 03.11.07 | C.W. | 25 | Bolangir | 15 | 10
|  |  |  | Total = | 25 |  | 15 | 10
12 | Creation of Addl. Facility in 16 ANM Training Centre, Bolangir. | 5.02 | D & FW (O) No. 6921 / 13.02.08 | C.W. | 10.02 | Bolangir | 5 | 5.02
|  |  |  | Total = | 10.02 |  | 5 | 5.02
|  | 43.09 |  |  | 95 |  | 51.91 | 43.09
13 | Impvt. to Ledies Hostel building of Dr. ACHMCH, Bhubaneswar. | 13.67 | DIMH No.13521 / 26.11.08 | C.W. | 33.34 | BBSR-I | 23 | 10.34
|  |  |  | E.I. | 3.33 | GED-I |  | 3.33
|  |  |  | P.H. | 3.33 | GPH-I | 3.33
|  |  |  | Total = | 40 |  | 26.33 | 13.67
14 | Expansion of Hospital building of ACHMCH. BBSR such as Improvement of Surgical Unit. | 20.32 | DIM&H No.11808 / 16.10.08 | C.W. | 36.68 | BBSR-I | 20.02 | 16.66 |  | NEW
|  |  |  | E.I. | 3.66 | GED-I |  | 3.66
|  |  |  | P.H. | 3.66 | GPH-I | 3.66
|  |  |  | Total = | 44 |  | 23.68 | 20.32
|  | 33.99 |  |  | 84 |  | 50.01 | 33.99
15 | S/R to Admn. Block main building at Capital Hospital, BBSR. | 0.19 |  | C.W. | 4.56 | BBSR-II | 4.37 | 0.19
|  |  |  | Total = | 4.56 |  | 4.37 | 0.19
16 | S/R to Renovation of East & North side block (medicine ward and casuality ward) of Capital Hospital. (weather coat to outside wall, repair to wall, chajja construction plinth protection, repair and replacement of choukatha and grills.) | 0.62 |  | C.W. | 3.79 | BBSR-II | 3.17 | 0.62
|  |  |  | Total = | 3.79 |  | 3.17 | 0.62
17 | S/R to C.T. Scan Cardiology, Ultra sound, Medicine female ward of Capital Hospital (South & West Block). (weather coat to outside wall, repair to wall, chajja construction plinth protection, repair and replacement of choukatha and grills.) | 1.09 |  | C.W. | 4.05 | BBSR-II | 2.96 | 1.09
|  |  |  | Total = | 4.05 |  | 2.96 | 1.09
18 | Repair to Special Cabin Kalayani Nursing Home at Capital Hospital. (white washing, distempering painting, wall plaster, celling plaster, replacement of window glass.) | 1.31 |  | C.W. | 3.64 | BBSR-II | 2.33 | 1.31
|  |  |  | Total = | 3.64 |  | 2.33 | 1.31
19 | S/R to O & G Ward in Capital Hospital. | 4.9 |  | C.W. | 4.9 | BBSR-II |  | 4.9
|  |  |  | Total = | 4.9 |  | 0 | 4.9
20 | S/R to Surgery Hospital Building at Capital Hospital in Unit-6. | 2.37 |  | C.W. | 4.55 | BBSR-II | 2.18 | 2.37
|  |  |  | Total = | 4.55 |  | 2.18 | 2.37
21 | Creation of Addl. Facility in 16 ANM Training Centre, BBSR. | 2.5 | D & FW (O) No. 6961 / 13.02.08 | C.W. | 10 | BBSR-II | 7.5 | 2.5
|  |  |  | Total = | 10 |  | 7.5 | 2.5
|  | 12.98 |  |  | 35.49 |  | 22.51 | 12.98
22 | Improvement of DHH at Bhawanipatna. | 13 | DHS (O) No.9551 / 03.11.07 | C.W. | 25 | Kalahandi | 12 | 13
|  |  |  | Total = | 25 |  | 12 | 13
|  | 13 |  |  | 25 |  | 12 | 13
23 | Improvement of DHH at Nuapada. | 13.5 | DHS (O) No.9544 / 03.11.07 | C.W. | 25 | Khariar | 11 | 13.5
|  |  |  | E.I. |  | GED-IV | 0.5
|  |  |  | Total = | 25 |  | 11.5 | 13.5
|  | 13.5 |  |  | 25 |  | 11.5 | 13.5
24 | Improvement of DHH at Nawarangpur. | 18.8 | DHS (O) No.10176 / 30.11.07 | C.W. | 23.8 | Jeypore | 5 | 18.8
|  |  |  | E.I. | 1.2 | GED-IV | 1.2
|  |  |  | Total = | 25 |  | 6.2 | 18.8
25 | Creation of Addl. Facility in 16 ANM Training Centre, Jeypore. | 7 | D & FW (O) No. 7375 / 15.02.08 | C.W. | 10 | Jeypore | 3 | 7
|  |  |  | Total = | 10 |  | 3 | 7
|  | 25.8 |  |  | 35 |  | 9.2 | 25.8
26 | Improvement of DHH at Boudha. | 15 |  | C.W. | 25 | Phulbani | 10 | 15
|  |  |  | Total = | 25 |  | 10 | 15
27 | Creation of Addl. Facility in 16 ANM Training Centre, Phulbani. | 10.55 | D & FW (O) No. 6931 / 13.02.08 | C.W. | 10.55 | Phulbani | 10 | 10.55
|  |  |  | Total = | 10.55 |  | 10 | 10.55
|  | 25.55 |  |  | 35.55 |  | 20 | 25.55
28 | Improvement to DHH of Sambalpur (such as const of 100 bedded ward ph - iv) 1st floor | 8.08 | DHS(O) No. 10182 / 30.11.07 | C.W. | 33.08 | Sambalpur | 25 | 8.08
|  |  |  | Total = | 33.08 |  | 25 | 8.08
|  | 8.08 |  |  | 33.08 |  | 25 | 8.08
29 | Creation of Addl. Facility in 16 ANM Training Centre, Dhenkanal. | 6 | D & FW (O) No. 6956 / 13.02.08 | C.W. | 12 | Denkanal | 6 | 6
|  |  |  | Total = | 12 |  | 6 | 6
|  | 6 |  |  | 12 |  | 6 | 6
30 | Creation of Addl. Facility in 16 ANM Training Centre, Balasore. | 10 | D & FW (O) No. 6941 / 13.02.08 | C.W. | 10 | Balasore |  | 10
|  |  |  | Total = | 10 |  | 0 | 10
|  | 10 |  |  | 10 |  | 0 | 10
31 | Creation of Addl. Facility in 16 ANM Training Centre, Daspalla, Nayagarh. | 5.04 | D & FW (O) No. 7380 / 15.02.08 | C.W. | 10.04 | Khurda | 5 | 5.04
|  |  |  | Total = | 10.04 |  | 5 | 5.04
|  | 5.04 |  |  | 10.04 |  | 5 | 5.04
32 | Creation of Addl. Facility in 16 ANM Training Centre, Puri. | 0.34 | D & FW (O) No. 6936 / 13.02.08 | C.W. | 10.34 | Puri | 10 | 0.34
|  |  |  | Total = | 10.34 |  | 10 | 0.34
|  | 0.34 |  |  | 10.34 |  | 10 | 0.34
| Grand Total = | 402 |  |  | 1116.5 |  | 798.68 | 402

## Finance_NP(M)_10-11
Statement showing Allotment of Funds for Building works of Finance Department (Non-Plan) for 2010-11
Rs. in Lakhs
Sl. No. | Head of Account, Name of the Work | B. P. 2010-11 | A.A.Cost With No. & Date |  |  | Name of (R&B) Division | Funds Allotted till 03/2010 |  | Funds alloted 2010-11 | Remarks
(1) | (2) | (3) | (4) |  |  | (5) | (6) |  | (7) | (8)
D. No-7-4059-N.P.
FINANCE DEPARTMENT
(A). C.T. Organisation
1 | Constn. of 1st floor over existing ground floor of the ACCT office, Puri Circle, Puri. | 4.8 | CCT memo No.3882 dt.4.3.09 | C.W | 24.06 | Puri | C.W | 24.06
|  |  |  | E.I | 2.4 | GED - I | E.I |  | 2.4
|  |  |  | P.H | 3.61 | GPHD - I | P.H | 1.2 | 2.4
|  |  |  | Total | 30.07 |  | Total | 25.26 | 4.8
2 | Constn. of Enforcement range office building at Balasore. | 71 | CCT memo No.8072 dt.13.5.10 | C.W | 69.93 | Balasore | C.W |  |  | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total | 69.93 |  | Total
3 | Improvement to CT Building at Bhubaneswar. | 14 | CCT memo No.15009 dt.12.8.09 | C.W | 32.9 | BBSR - IV | C.W | 18.9 | 14
|  |  |  | E.I | 3.26 | GED - I | E.I | 3.26
|  |  |  | P.H | 4.89 | GPHD - I | P.H | 4.89
|  |  |  | Total | 41.05 |  | Total | 27.05 | 14
4 | Constn. of boundary wall at Laxmannath Road check gate at 50/200 km to 51/200 km on NH 60. | 338.59 |  | C.W |  |  | C.W
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
5 | Constn. of office building at Laxmannath Road check gate. | 100 |  | C.W |  |  | C.W
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
6 | Constn. of office building at Girisola check gate. | 200 |  | C.W |  |  | C.W
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
7 | Area lighting around the Unified check gate, Jamsolaghat. | 40.44 | CCT memo No.8118 dt.13.5.10 | C.W |  |  | C.W
|  |  |  | E.I | 40.44 | GED - II | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total | 40.44 |  | Total
8 | Constn. of Masonary compound wall and site development at Girisola check gate. | 153.1 |  | C.W |  |  | C.W
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
9 | Construction of non residential buildings under Commissioner of Commercial Taxes. | 50 |  | C.W |  |  | C.W |  | 21.536 | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total |  | 21.536
10 | Improvement of Nalda check gate | 100 |  | C.W |  |  | C.W |  |  | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
11 | Improvement of Champua check gate. | 100 |  | C.W |  |  | C.W
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
12 | Improvement of check gate at Bileipada in Keonjhar District. | 50 |  | C.W |  |  | C.W
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
13 | Constn. of newly created Angul Range office over the Angul Circle office building. | 50 | CCT memo No.11222 dt.3.7.10 | C.W |  | Angul | C.W |  | 50 | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total | 109.54 |  | Total |  | 50
14 | Constn. of office building of Gajapati Circle, Paralakhemundi, Gajapati District. | 50 |  | C.W |  | Paralakhemundi | C.W |  |  | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
15 | Supply and installation of high mast lighting system at Laxmannath Road check gate on NH 60. | 6.67 | CCT memo No.6158 dt.6.4.10 | C.W |  |  | C.W
|  |  |  | E.I | 6.67 | GED - II | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total | 6.67 |  | Total
16 | Constn. of 100KVA 11/4 KV Substation at Laxmannath Road check gate on NH 60 | 6.71 | CCT memo No.6158 dt.6.4.10 | C.W |  |  | C.W
|  |  |  | E.I | 6.68 | GED - II | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total | 6.68 |  | Total
17 | Provision of street lights both side of road at Laxmannath Road check gate on NH 60 | 4.82 | -do- | C.W |  |  | C.W
|  |  |  | E.I | 4.82 | GED - II | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total | 4.82 |  | Total
18 | Constn. of LT line using 9 mt long PSC pole (300) for street light and power suppsy to proposed site at Laxmannath Road check gate on NH 60. | 11.06 | -do- | C.W | 11.06 | GED - II | C.W
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total | 11.06 |  | Total
19 | Improvement of office building of ACCT, Nuapada Circle, Khariar Road. | 8 | CCT memo No.11230 dt.3.7.10 | C.W | 8 | Khariar | C.W |  | 8 | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total | 8 |  | Total |  | 8
20 | Improvement of ACCT office building Mayurbhanj Circle. Baripada such as portico, compound wall, plinth protection and levelling of ground. | 8.02 | CCT memo No.8125 dt.13.5.10 | C.W | 8.02 | Mayurbhanj | C.W |  | 8.02 | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total | 8.02 |  | Total |  | 8.02
21 | E/I to conference hall at ACCT office building Balasore Circle, Balasore. | 3.8 | CCT memo No.11209 dt.3.7.10 | C.W |  |  | C.W |  |  | NEW
|  |  |  | E.I | 3.8 | GED - II | E.I |  | 3.8
|  |  |  | P.H |  |  | P.H
|  |  |  | Total | 3.8 |  | Total |  | 3.8
22 | Renovation of Banijyakar Bhawan inside old Secretariat area at Cuttack. | 5.52 | CCT memo No.10666 dt.26.6.10 | C.W | 5.52 | Cuttack | C.W |  | 5.52 | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total | 5.52 |  | Total |  | 5.52
23 | Construction of 3rd floor of CTD office building at Rourkela. | 15 | CCT memo No.8086 dt.13.5.10 | C.W | 81.47 | Rourkela | C.W |  | 15 | NEW
|  |  |  | E.I | 8.15 | GED - III | E.I
|  |  |  | P.H | 8.15 | GPHD - II | P.H
|  |  |  | Total | 97.77 |  | Total |  | 15
24 | Construction of compound wall of JCCT office at Jajpur road. | 5.33 | CCT memo No.8391 dt.18.5.10 | C.W | 5.33 | Panikoile | C.W |  | 5.33 | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total | 5.33 |  | Total |  | 5.33
25 | Construction of cycle stand etc. of JCCT Range office jajpur road. | 1.88 | CCT memo No.8384 dt.18.5.10 | C.W | 1.876 | Panikoile | C.W |  | 1.88 | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total | 1.876 |  | Total |  | 1.88
26 | Construction of temporary shed and loop road at Girisola. | 50.15 |  | C.W |  |  | C.W
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
27 | Construction of office building at Lahurachati Checkgate. | 100 |  | C.W |  |  | C.W
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
28 | Shifting of Kanaktora Checkgage to Govindpur and improvement of Checkgate infrastructure at new site (Office building, loop road etc.) | 100 |  | C.W |  |  | C.W
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
29 | Improvement of infrastructure of Biramitrapur Checkgate (Construction of office building etc.) | 50 |  | C.W |  |  | C.W
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
30 | Shifting of Sunki Checkgate to Patangi (Infrastructural development.) | 20 |  | C.W |  |  | C.W
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
31 | Construction of Banijyakar Bhawan, Cuttack (Balance work) | 34.81 | RAA FID No.22922 dt.19.5.07 | C.W | 1100.99 | Cuttack | C.W | 1066.18 | 34.81
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total | 1100.99 |  | Total | 1066.18 | 34.81
32 | Construction of new office building of Assessement Unit at Jajpur town. | 18 | CCT memo No.21266 dt.7.11.09 | C.W | 24.05 | Panikoile | C.W | 12 | 12.05 | NEW
|  |  |  | E.I | 2.38 | GED - II | E.I |  | 2.38
|  |  |  | P.H | 3.57 | GPHD - I | P.H |  | 3.57
|  |  |  | Total | 30 |  | Total | 12 | 18
| Total = | 1771.7 | [6 empty] | 190.696
(B). Treasury Organisation
1 | Construction of Special Treasury No.I, Bhubaneswar. | 0.01 | Finance Deptt. No.37121 dt.1.9.06 | C.W | 191.4 | BBSR - I | C.W | 222.21
|  |  |  | E.I | 71.45 | GED - I | E.I | 71.45
|  |  |  | P.H | 16.58 | GPHD - I | P.H | 12.57
|  |  |  | Total | 279.43 |  | Total | 306.23
2 | Improvement of Sub-Treasury office building at Bhuban. | 18.89 | DTI memo No.17339 dt.26.10.09 | C.W | 24.08 | Dhenkanal | C.W | 10 | 14.09
|  |  |  | E.I | 2.4 | GED - II | E.I |  | 2.4
|  |  |  | P.H | 2.4 | GPHD - II | P.H |  | 2.4
|  |  |  | Total | 28.88 |  | Total | 10 | 18.89
3 | Construction of Sub-Treasury office building at Dhamnagar. | 19.81 | DTI memo No.12933 dt.10.8.09 | C.W | 29.87 | Bhadrak | C.W | 17 | 12.87
|  |  |  | E.I | 2.98 | GED - II | E.I | 0.5 | 2.38
|  |  |  | P.H | 8.96 | GPHD - I | P.H | 2 | 4.56
|  |  |  | Total | 41.81 |  | Total | 19.5 | 19.81
4 | Construction of Sub-Treasury office building at Jatni. | 5 | DTI memo No.17363 dt.26.10.09 | C.W | 24.36 | BBSR - II | C.W | 5 | 5 | NEW
|  |  |  | E.I | 2.44 | GED - I | E.I
|  |  |  | P.H | 2.44 | GED - II | P.H
|  |  |  | Total | 29.24 |  | Total | 5 | 5
5 | Construction of Inspection room-cum-Guest House for District Treasury Nuapada. | 4 | DTI memo No.7789 dt.20.5.10 | C.W | 3.08 | Khariar | C.W |  | 3.08 | NEW
|  |  |  | E.I | 0.26 | GED - IV | E.I |  | 0.26
|  |  |  | P.H | 0.66 | GPH - II | P.H |  | 0.66
|  |  |  | Total | 4 |  | Total |  | 4
6 | Power supply of 2 x 5 KW load to Sub-Trasury office at Kotpad. | 2.39 | DTI memo No.7781 dt.20.5.10 | C.W |  |  | C.W |  |  | NEW
|  |  |  | E.I | 2.39 | GED - IV | E.I |  | 2.39
|  |  |  | P.H |  |  | P.H
|  |  |  | Total | 2.39 |  | Total |  | 2.39
7 | Construction of compound wall and repair of Sub-Trasury office building at Soro. | 7.19 | DTI memo No.7773 dt.20.5.10 | C.W | 7.1 | Balasore | C.W |  | 7.19 | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total | 7.1 |  | Total |  | 7.19
8 | External water supply to Sub-Treasury office building at Hinjlicut. | 2.04 | DTI memo No.7785 dt.20.5.10 | C.W |  |  | C.W |  |  | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H | 2.04 | GPHD - I | P.H |  | 2.04
|  |  |  | Total | 2.04 |  | Total |  | 2.04
9 | Provision for Fire Extinguisher for Treasury & Accounts Bhawan. | 5.79 | DTI memo No.8290 dt.1.6.10 | C.W |  |  | C.W
|  |  |  | E.I | 5.79 | GED - I | E.I |  | 5.79
|  |  |  | P.H |  |  | P.H
|  |  |  | Total | 5.79 |  | Total |  | 5.79
10 | Construction of boundary wall for Sub-Treasury office building at Purusottampur. | 5.36 | CCT memo No.7795 dt.21.5.10 | C.W | 5.36 | Ganjam - II | C.W |  | 5.36 | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total |  | 5.36
11 | Improvement of Sub-Treasury office building at Hindol. | 4.85 | DTI memo No.8083 dt.27.5.10 | C.W | 4.69 | Dhenkanal | C.W |  | 4.85 | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total |  | 4.85
12 | S/F of 800 Amp MOCB panel board at main control room of Treasury & Accounts Bhawan, Bhubaneswar. | 4.75 | DTI memo No.8292 dt.1.6.10 | C.W |  |  | C.W |  |  | NEW
|  |  |  | E.I | 4.74 | GED - I | E.I |  | 4.75
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total |  | 4.75
13 | Supply & fixing of 100 KVA silent DG sets for 2nos of lifts at Treasur & Accounts Bhawan, Bhubaneswar. | 9 |  | C.W |  |  | C.W |  |  | NEW
|  |  |  | E.I |  | GED - I | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
14 | Construction of District Treasury building at Baragarh. | 16.47 | DTI memo No.3331 dt.18.02.10 | C.W | 83.38 | Baragarh | C.W | 66.9 | 16.47
|  |  |  | E.I | 6.68 | GED - III | E.I | 6.68
|  |  |  | P.H | 16.73 | GPH - II | P.H | 16.73
|  |  |  | Total | 106.79 |  | Total | 90.31 | 16.47
15 | Construction of Sub-Treasury office building at Dharmagarh. | 15.33 | R.A.A. DTI memo No.7777 dt.20.5.10 | C.W | 36.53 | Kalahandi | C.W | 23.76 | 12.77
|  |  |  | E.I | 3.65 | GED - IV | E.I | 2.38 | 1.27
|  |  |  | P.H | 4.24 | GPHD - II | P.H | 2.95 | 1.29
|  |  |  | Total | 44.42 |  | Total | 29.09 | 15.33
16 | Construction of Sub-Treasury building at Bhanjanagar, Ganjam. | 50 | DTI memo No.5359 dt.28.6.10 | C.W | 33.93 | Bhanjanagar | C.W |  | 33.93 | NEW
|  |  |  | E.I | 2.48 | GED - I | E.I |  | 2.48
|  |  |  | P.H.(Int) | 2.48 | GPHD - I | P.H |  | 6.21
|  |  |  | P.H.(Ext) | 3.73
|  |  |  | Total | 42.62 |  | Total |  | 42.62
17 | Supply and laying of cable, DB, MCB, Modular switch and socket etc. for Nerve Centre, 2nd floor, DT & I, Bhubaneswar. | 5.42 |  | C.W |  |  | C.W |  |  | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
18 | Provision of Automatic Fire Protection system / Detection system / Alarm system at Nerve Centre, 2nd floor, DT & I, Bhubaneswar. | 3.45 |  | C.W |  |  | C.W |  |  | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
19 | Supply & laying of cable and panel board for the Nerve Centre, 2nd floor, DT & I, Bhubaneswar. | 5.88 |  | C.W |  |  | C.W |  |  | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
20 | Supply and installation of Aplab make on-Line UPS system (20KVA) with MF battery backup in the Computer Narve Centre for Cyber Treasury at DT & I, Bhubaneswar. | 25.35 |  | C.W |  |  | C.W |  |  | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
21 | Provision of AFA panel 200 Amp charge over chemical earting. I.O. Bod Bub panel LAN connector wiring etc. DT & I, Bhubaneswar. | 5.08 |  | C.W |  |  | C.W |  |  | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
22 | S/F of computer point at Cyber Treasury, 6th floor of Treasury & Accounts Bhawan, 2nd floor, DT & I, Bhubaneswar. | 0.17 |  | C.W |  |  | C.W |  |  | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
23 | S/F of 62.5 KVA DG sets with AMF panel for Nerve Centre 2nd floor, Treasury & Accounts Bhawan, Bhubaneswar. | 9.84 |  | C.W |  |  | C.W |  |  | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
24 | Provision of 2nos of split type 1.5 ton AC with power supply at Cyber Treasury, 6th floor, Treasury & Accounts Bhawan, Bhubaneswar. | 0.97 |  | C.W |  |  | C.W |  |  | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
25 | Re-installation, shifting of 6 nos split A/C machine including angle platform at Nerve Centre, 2nd floor, DT & I, Orissa, Bhubaneswar. | 3.29 |  | C.W |  |  | C.W |  |  | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
26 | Renovation and servicing of 4nos 7.5 ton package unit at Nerve Centre, DT & I, Bhubaneswar. | 1.32 |  | C.W |  |  | C.W |  |  | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
27 | S/F of 2nos of 3 ton sleem pack with power supply system at Nerve Centre, 2nd floor, DT & I, Bhubaneswar. | 3.76 |  | C.W |  |  | C.W |  |  | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
| Total = | 235.41 | [6 empty] | 154.49
(C).Controller of Accounts
1 | Installation of work stations, Help desk etc. in the o/o the Controller of Accounts (Balance work) | 9.06 |  | C.W |  | BBSR - I | C.W
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
| Total = | 9.06
(D). Local Fund Audit Organisation
1 | Improvement to Audit office of LFA, Sundargarh. | 4.5 | Finance Deptt. No.4133 dt.2.6.10 | C.W | 4.5 | Sundargarh | C.W |  | 4.5 | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total | 4.5 |  | Total |  | 4.5
2 | Improvement to office building of DAO, Local Fund Addit, Mayurbhanj, Baripada. | 1.24 | Finance Deptt. No.1100 dt.6.02.09 | C.W | 6.77 | Mayurbhanj | C.W | 5.53 | 1.24
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total | 6.77 |  | Total | 5.53 | 1.24
3 | Construction of office building of DAO, Cuttack. | 100 | Finance Deptt. No.34 dt.2.01.10 | C.W | 170.73 | Cuttack | C.W | 15 | 90 | NEW
|  |  |  | E.I | 42.27 | GED - II | E.I |  | 5
|  |  |  | P.H | 42.27 | GPHD - I | P.H |  | 5
|  |  |  | Total | 255.27 |  | Total | 15 | 100
| Total = | 105.74 | [6 empty] | 105.74
(E). M.D.R.A.F.M.
1 | Construction of a separte Guest house for resource persons. | 89.92 | MDRAFM No.2467 dt.13.11.07 | C.W | 157.3 | BBSR - III | C.W | 119.84 | 37.46
|  |  |  | E.I | 23.52 | GED - I | E.I | 5 | 18.52
|  |  |  | P.H | 18.94 | GPHD - I | P.H | 5 | 13.94
|  |  |  | Total | 199.76 |  | Total | 129.84 | 69.92
2 | Renovation of old library rooms in MDRAFM. | 1.79 | MDRAFM No.1658 dt.14.7.10 | C.W | 1.786 | BBSR - III | C.W |  | 1.79 | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total | 1.786 |  | Total |  | 1.79
| Total = | 91.71 | [6 empty] | 71.71
| Total (Finance) = | 2213.62 | [6 empty] | 522.636
D. No-7-4216-N.P.
FINANCE DEPARTMENT
(I). C.T. Organisation
1 | Improvement and renovation to the compound wall of CTO staff colony, Bhawanipatna, Kalahandi. | 5 | CCT memo No.8398 dt.18.5.10 | C.W | 5 | Kalahandi | C.W |  | 5 | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total | 5 |  | Total |  | 5
2 | Improvement to 11nos. of CTO staff quarters at Bhawanipatna, Kalahandi. | 33.4 | CCT memo No.8405 dt.18.5.10 | C.W | 38.4 | Kalahandi | C.W |  | 29.95 | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  | GPHD - II | P.H |  | 3.45
|  |  |  | Total | 38.4 |  | Total |  | 33.4
3 | Improvement to 14nos. of CTO staff quarters at Bhawanipatna, Kalahandi. | 43.84 | CCT memo No.8412 dt.18.5.10 | C.W | 48.87 | Kalahandi | C.W |  | 39.45 | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  | GPHD - II | P.H |  | 4.39
|  |  |  | Total | 48.87 |  | Total |  | 43.84
4 | Construction of residential buildings of C.T. organisation. | 50 |  | C.W |  |  | C.W |  | 13.199 | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total |  | 13.199
5 | Construction of quarters of JCCT & DCCT of Angul Range, Angul. | 5 | CCT memo No.11216 dt.3.7.10 | C.W | 39.08 | Angul | C.W |  | 5 | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total | 39.08 |  | Total |  | 5
6 | Cement painting to outside wall of staff quarters at new LIC colony, Badambadi, Cuttack (Block G,H,I,E,F,J,K,L,M,N,O,P,Q, & R) | 3.87 | CCT memo No.1426 dt.28.6.10 | C.W | 3.87 | Cuttack | C.W |  | 3.87 | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total | 3.87 |  | Total |  | 3.87
7 | Improvement to Block G,H,I such as raising of floor of staff quarters at new LIC colony, Badambadi, Cuttack. | 3.08 |  | C.W |  | Cuttack | C.W |  |  | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
8 | Improvement to Electrical installation work to 7nos of C.T. staff quarters at Bhadrak. | 2.49 |  | C.W |  |  | C.W |  |  | NEW
|  |  |  | E.I |  | GED - II | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
9 | Renovation, alteration to existing 2nos of ACTO quarters at Bhadrak. | 2.8 |  | C.W |  | Bhadrak | C.W |  |  | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
10 | Improvement to CTD staff quarters 2RB 1,2,3,4,7 2RFG- 1,2,3,4, 2RFH-1,2,3,4 and 2RL-1,2,3 of JCCT Range office at Jajpur road. | 1.79 | CCT memo No.8363 dt.18.5.10 | C.W | 1.792 | Panikoile | C.W |  | 1.79 | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total | 1.792 |  | Total |  | 1.79
11 | Cosntruction of quarter for W.C.S of C.T.O. A/U Rairangpur. | 2.9 | CCT memo No.8110 dt.13.5.10 | C.W | 2.9 | Rairangpur | C.W |  | 2.9 | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total | 2.9 |  | Total |  | 2.9
12 | Improvement to CTD staff quarters 3RA-1,2,3 & 3RB-1 of JCCT Range office at Jajpur road. | 2.83 | CCT memo No.8377 dt.18.5.10 | C.W | 2.827 | Panikoile | C.W |  | 2.83 | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total | 2.827 |  | Total |  | 2.83
13 | Improvement to CTD staff quarters 2RA-1,2,3 of JCCT Range office at Jajpur road. | 2.73 | CCT memo No.8370 dt.18.5.10 | C.W | 2.7323 | Panikoile | C.W |  | 2.73 | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total | 2.7323 |  | Total |  | 2.73
14 | Improvent to staff quarters of CTD at Balasore Range (Part-A flooring and plastering) | 5 | CCT memo No.8342 dt.18.5.10 | C.W | 4.997 | Balasore | C.W |  | 5 | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total | 4.997 |  | Total |  | 5
15 | Improvent of staff quarters of CTD at Balasore Range (Part-B cement concrete & plinth protection work) | 4.99 | CCT memo No.8349 dt.18.5.10 | C.W | 4.9893 | Balasore | C.W |  | 4.99 | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total | 4.9893 |  | Total |  | 4.99
16 | Improvent of staf quarters of CTD at Balasore Range (Part-C for wooden fixture and colouring work.) | 4.97 | CCT memo No.8356 dt.18.5.10 | C.W | 4.973 | Balasore | C.W |  | 4.97 | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total | 4.973 |  | Total |  | 4.97
17 | Construction of residential quarters for staff of CT organisation of Unit 39, Rourkela. | 131.73 | F/D No.34569 dt.14.8.07 | C.W | 238.35 | Rourkela | C.W | 155.21 | 83.14 | NEW
|  |  |  | E.I | 31.62 | GED - III | E.I | 19.08 | 12.54
|  |  |  | P.H | 54.05 | GPHD - II | P.H | 18 | 36.05
|  |  |  | Total | 324.02 |  | Total | 192.29 | 131.73
| Total = | 306.42 | [6 empty] | 261.249
(II). Treasury Organisation
1 | Construction of one 'F' type quarter for staff of Sub-Treasury office, Bhograi. | 0.79 | DTI memo No.18808 dt.18.11.09 | C.W | 4.74 | Balasore | C.W | 3.95 | 0.79
|  |  |  | E.I | 0.47 | GED - II | E.I | 0.47
|  |  |  | P.H | 0.47 | GPHD - I | P.H | 0.47
|  |  |  | Total | 5.68 |  | Total | 4.89 | 0.79
2 | Construction of compound wall for the staff quarters of the Sub-Treasury at Biramitrapur. | 5.97 | DTI memo No.8091 dt.27.5.10 | C.W | 5.97 | Rourkela | C.W |  | 5.97 | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total | 5.97 |  | Total |  | 5.97
3 | Construction of compound wall and approach road to staff quarters at Sub-Treasury office, Rajgangpur. | 6.08 | DTI memo No.8087 dt.27.5.10 | C.W | 6.08 | Sundargarh | C.W |  | 6.08 | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total | 6.08 |  | Total |  | 6.08
4 | Improvent of two nos 'F' type quarters for Sub-Treasury office building at Rajgangpur. | 3.7 |  | C.W |  | Sundargarh | C.W |  |  | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
5 | Construction of 2nos 'F' type quarters for the staff of District Treasury, Sambalpur. | 17.49 | DTI memo No.8834 dt.10.6.10 | C.W | 13.23 | Sambalpur | C.W |  | 13.26 | NEW
|  |  |  | E.I | 1.2 | GED - III | E.I |  | 1.21
|  |  |  | P.H | 3.01 | GPHD - II | P.H |  | 3.02
|  |  |  | Total | 17.44 |  | Total |  | 17.49
6 | Construction of 2nos 'E' type and and 2nos of 'F' type quarters of Sub-Treasury, Nimapara. | 21.86 | DTI memo No.19213 dt.16.10.07 | C.W | 19.45 | Puri | C.W | 2.45 | 17
|  |  |  | E.I | 1.94 | GED - I | E.I |  | 1.94
|  |  |  | P.H | 2.92 | GPHD - I | P.H |  | 2.92
|  |  |  | Total | 24.31 |  | Total | 2.45 | 21.86
7 | Construction of one 'D' type 2nos of 'E' type and 2nos of 'F' type quarters for staff of District Treasury, Sundargarh. | 15.13 |  | C.W |  | Sundargarh | C.W
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
8 | Construction of one 'D' type 2nos of 'E' type quarters for staff of Sub-Treasury, Udala. | 6.07 | DTI memo No.18997 dt.21.11.09 | C.W | 23.24 | Mayurbhanj | C.W | 15 | 6.07
|  |  |  | E.I | 2.32 |  | E.I
|  |  |  | P.H | 3.49 |  | P.H
|  |  |  | Total | 29.05 |  | Total | 15 | 6.07
| Total = | 77.09 | [6 empty] | 58.26
(III). M.D.R.A.F.M.
1 | Construction of 12nos of 'F' type staff quarters of MDRAFM | 11.48 | R.A.A. MDRAFM No.533 dt.2.3.10 | C.W | 41.2 | BBSR - III | C.W | 33.66 | 7.7
|  |  |  | E.I | 4.12 | GED - I | E.I | 3.31 | 0.81
|  |  |  | P.H | 7.58 | GPHD - I | P.H | 4.96 | 2.97
|  |  |  | Total | 52.9 |  | Total | 41.93 | 11.48
| Total = | 11.48 | [6 empty] | 11.48
| Total (Finance) = | 394.99 | [6 empty] | 330.989

## G.A. (Vig.)_4216_NP(M)
Statement showing B.P. / Allotment of Funds for Residential Building works under N.P. (Major) G.A. (Vig.) Deptt. for 2010-11
Rs. in Lakhs
Sl. No. | Head of Account, Name of the Work | B. P. 2010-11 |  | A.A.Cost With No. & Date |  |  | Name of Division | Funds Allotted till 03/2010 |  | Funds alloted 2010-11 |  | Expdr. | Physical Progress | Remarks
|  | O.B.P. | 1st Suppl. | [6 empty] | O.B.P. | 1st Suppl.
(1) | (2) | (3) |  | (4) |  |  | (5) | (6) |  | (7) |  | (8) | (9) | (10)
D. No-7-4216-Col-on-Housing-01-GRB-106-GPA
G.A. Vigilance Department
1 | Constn. of 2 nos. "C" type qtrs. of Vigilance Unit office at Jajpur. | 14.8 |  | No. 145 dt. 6-1-10 | C.W. | 29.52 | Panikoili | 09-10 | 15 | 10
[5 empty] | E.I. | 2.523 | G.E.D.-II |  |  | 2
[5 empty] | P.H. | 3.784 | G.P.H.-I |  |  | 2.8
|  |  |  | Total |  | 35.827 |  |  | 15 | 14.8 | 0
2 | Constn. of 2 nos. "C" type qtrs. of Vigilance Unit office at Kendrapara. | 9.8 |  | No. 623 dt. 30-1-10 | C.W. | 30.514 | Kendrapara | 09-10 | 20 | 7.8
[5 empty] | E.I. | 3.052 | G.E.D.-II |  |  | 1
[5 empty] | P.H. | 3.052 | G.P.H.-I |  |  | 1
|  |  |  | Total |  | 36.618 |  |  | 20 | 9.8 | 0
3 | Constn. of 2 nos. "C" type qtrs. of Vigilance Unit office at Subarnapur. | 4.8 |  | No. 9368 dt. 31-12-09 | C.W. | 30.214 | Bolangir | 09-10 | 5 | 4.8
[5 empty] | E.I. | 3.022
[5 empty] | P.H. | 3.022
|  |  |  | Total |  | 36.258 |  |  | 5 | 4.8 | 0
4 | Constn. of 2 nos. "C" type qtrs. of Vigilance Unit office at Nabarangapur. | 19.8 |  | No- 9377 dt-31-12-09 | C.W. | 26.557 | Jeypore |  |  | 17.8
[5 empty] | E.I. | 2.519 | G.E.D.-IV |  |  | 1
[5 empty] | P.H. | 3.779 | G.P.H.-II |  |  | 1
|  |  |  | Total |  | 32.855 |  |  | 0 | 19.8 | 0
5 | Constn. of 2 nos. "C" type qtrs. of Vigilance Unit office at Nuapada. | 24.8 |  | No. 641 dt. 30-1-10 | C.W. |  | Khariar | 09-10 | 5 | 23
[5 empty] | E.I. |  | G.E.D.-IV |  |  | 0.8
[5 empty] | P.H. |  | G.P.H.-II |  |  | 1
|  |  |  | Total |  | 40.274 |  |  | 5 | 24.8 | 0
6 | Constn. of 2 nos. "F" type qtrs. of Vigilance Unit office at Jajpur. | 6.2 |  | No. 145 dt. 6-1-10 | C.W. | 14.391 | Panikoili | 09-10 | 5 | 6.2
[5 empty] | E.I. | 1.23
[5 empty] | P.H. | 1.845
|  |  |  | Total |  | 17.466 |  |  | 5 | 6.2 | 0
7 | Constn. of 2 nos. "F" type qtrs. of Vigilance Unit office at Nabarangapur. | 6.2 |  | A.A. Cost 17.802 No- 9377 dt-31-12-09 | C.W. | 14.31 | Jeypore | 09-10 | 5 | 6.2
[5 empty] | E.I. | 1.365
[5 empty] | P.H. | 2.05
|  |  |  | Total |  | 17.725 |  |  | 5 | 6.2 | 0
8 | Constn. of 2 nos. "F" type qtrs. of Vigilance Unit office at Nuapada. | 6.2 |  | No. 641 dt. 30-1-10 | C.W. |  | Khariar | 09-10 | 5 | 6
[5 empty] | E.I. |  | G.E.D.-IV |  |  | 0.2
P.H.
|  |  |  | Total |  | 14.082 |  |  | 5 | 6.2 | 0
9 | Construction of 4 (Four) nos. of "F" type qtrs. of Vigilance Unit Office at Jagatsinghpur. | 30 |  | No- 4697 dt- 10-5-10 | C.W. | 25.45 | Jagatsinghpur |  |  | 24 |  |  |  | NEW
[5 empty] | E.I. | 3.78 | G.E.D.-IV |  |  | 3
[5 empty] | P.H. | 3.78 |  |  |  | 3
|  |  |  | Total |  | 33.01 |  |  | 0 | 30 | 0
10 | Construction of 2 (two) nos. of "C" type qtrs. of Vigilance Unit Office at Paralakhemundi. | 30 |  | Estimated Cost | C.W. | 38.331 | Paralakhemundi |  |  | 27 |  |  |  | NEW
[5 empty] | E.I. | 3.833 | G.E.D.-I |  |  | 1.5
[5 empty] | P.H. | 3.833 | G.P.H.-I |  |  | 1.5
|  |  |  | Total |  | 45.997 |  |  | 0 | 30 | 0
A.A. Limited to Rs.30.00 lakhs No-5693 dt. 1.7.10
11 | Construction of 4 (Four) nos. of "F" type qtrs. of Vigilance Unit Office at Paralakhemundi. | 30 |  | Estimated Cost | C.W. | 28.166 | Paralakhemundi |  |  | 26.5 |  |  |  | NEW
[5 empty] | E.I. | 2.817 | G.E.D.-I |  |  | 1.5
[5 empty] | PH(I) | 2.817 | G.P.H.-I |  |  | 1
[5 empty] | PH(E) | 3.38 | G.P.H.-I |  |  | 1
|  |  |  | Total |  | 37.18 |  |  | 0 | 30 | 0
A.A. Limited to Rs.30.00 lakhs No-5693 dt. 1.7.10
12 | Construction of 2 (two) nos. of "C" type qtrs. of Vigilance Unit Office at Boudh. | 30 |  | Estimated Cost | C.W. | 30.606 | Phulbani |  |  | 27 |  |  |  | NEW
[5 empty] | E.I. | 3.061 | G.E.D.-IV |  |  | 1.5
[5 empty] | PH | 3.061 | G.P.H.-II |  |  | 1.5
|  |  |  | Total |  | 36.728 |  |  | 0 | 30 | 0
A.A. Limited to Rs.30.00 lakhs No-5703 dt. 1.7.10
13 | Construction of 4 (Four) nos. of "F" type qtrs. of Vigilance Unit Office at Boudh. | 30 |  | No. 4514 dt. 14-5-10 | C.W. | 30.08 | Phulbani |  |  | 28 |  |  |  | NEW
[5 empty] | E.I. | 3.01 | G.E.D.-IV |  |  | 1
[5 empty] | P.H. | 3.01 | G.P.H.-II |  |  | 1
|  |  |  | Total = |  | 36.1 |  |  |  | 30
14 | Construction of 4 (Four) nos. of "F" type qtrs. of Vigilance Unit Office at Sundargarh. | 30 |  | No. 4702 dt. 20-5-10 | C.W. | 25.04 | Sundargarh |  |  | 25.04 |  |  |  | NEW
[5 empty] | E.I. | 2.48 | G.E.D.-III |  |  | 2.48
[5 empty] | P.H. | 2.48 | G.P.H.-II |  |  | 2.48
|  |  |  | Total = |  | 30 |  |  |  | 30
15 | Construction of 2 (Two) nos. of "C" type qtrs. of Vigilance Unit Office at Jagatsinghpur | 30 |  |  | C.W. |  | Jagatsinghpur | [6 empty] | NEW
[5 empty] | E.I. |  | G.E.D.-II
[5 empty] | P.H. |  | G.P.H.-I
|  |  |  | Total = |  | 0 |  |  |  | 0
16 | Construction of 2 (Two) nos. of "C" type qtrs. of Vigilance Unit Office at Baripada. | 30 |  | No- 5586 dt-28-06-10 | C.W. | 31.974 | Mayurbhanj |  |  | 27 |  |  |  | NEW
[5 empty] | E.I. | 3.197 | G.E.D.-II |  |  | 1.5
[5 empty] | P.H. | 3.197 | G.P.H.-I |  |  | 1.5
|  |  |  | Total = |  | 38.368 |  |  |  | 30
17 | Construction of 4 (Four) nos. of "F" type qtrs. of Vigilance Unit Office at Baripada. | 30 |  | No- 5586 dt-28-06-10 | C.W. | 28.423 | Mayurbhanj |  |  | 27 |  |  |  | NEW
[5 empty] | E.I. | 2.842 | G.E.D.-II |  |  | 1.5
[5 empty] | P.H. | 2.842 | G.P.H.-I |  |  | 1.5
|  |  |  | Total = |  | 34.107 |  |  |  | 30
18 | Construction of 4 (Four) nos. of "F" type qtrs. of Vigilance Unit Office at Bhawanipatana. | 30 |  | Estimated Cost | C.W. | 28.823 | Kalahandi |  |  | 27 |  |  |  | NEW
[5 empty] | E.I. | 2.882 | G.E.D.-IV |  |  | 1.5
[5 empty] | PH | 2.882 | G.P.H.-II |  |  | 1.5
|  |  |  | Total |  | 34.587 |  |  | 0 | 30 | 0
A.A. Limited to Rs.30.00 lakhs No-5698 dt. 1.7.10
19 | Constn. of 2 nos. "C" type qtrs. of Vigilance Unit office at Nayagarh |  |  | Ltr. No-454 dt-25-1-10 | C.W. | 30.548 | Khurda
[5 empty] | E.I. | 3.05
[5 empty] | P.H. | 7.588
|  |  |  | Total |  | 41.186 |  |  |  | 0 | 0
20 | Constn. of 2 nos. "F" type qtrs. of Vigilance Unit office at Subarnapur. |  |  | No. 9368 dt. 31-12-09 | C.W. | 14.555 | Bolangir
[5 empty] | E.I. | 1.455
[5 empty] | P.H. | 1.456
|  |  |  | Total |  | 17.466 |  |  |  | 0 | 0
| Total = | 392.6 |  |  |  | 615.834 |  |  |  | 362.6

## H.E.-NP(M)
NON PLAN (MAJOR)
Statement Showing the Building works for the year 2010-2011 Name of the Department :- Higher Education
(Rs. In Lakhs)
Sl. No. | Name of the Work | O.B. P | 1st Suppl. | A.A. Cost | Name of the (R&B) Divison | Allotment up to 03/2010 | Allottment 2010-11 | Expdr. | Physical Progress | Remarks
(1) | (2) | (3) |  | (4) | (5) | (6) | (7) | (8) | (9) | (10)
HIGHER DUCATION DEPARTMENT
4059 NON-PLAN (MAJOR)
1 | Construction of Girl's Hostel at Bhadrak College, Bhadrak. | 150 |  | 200.00 No. 50703 dt-30-11-07 | Bhadrak | 50 | 50 |  |  | NEW

## C.P.-4202
DETAILED LIST OF CENTRAL PLAN SCHEMES (SCHOOL & MASS EDUCATION DEPARTMENT)
(Rs. In Lakhs)
Sl. No | Name of the Works | O.B.P. | 1st Suppl. | A.A. Cost | Name of the (R&B) Divison | Allotment up to 03/2010 | Allottment 2010-11 | Expdr. | Physical Progress | Remarks
(1) | (2) | (3) |  | (4) | (5) | (6) | (7) | (8) | (9) | (10)
SCHOOL & MASS DEPARTMENT
1 | Construction of Administrative / Institution Building of DIET, Kendrapara at Balia. | 45
2 | Construction of Administrative / Institution Building of DIET, Jagatsinghpur. | 75
3 | Construction of Administrative / Institution Building of DIET, Angul at Chhendipada. | 45
4 | Construction of Administrative / Institution Building of DIET, Nayagarh at Rajsunakhala. | 45
5 | Construction of Administrative / Institution Building of DIET, Bhadark at Agarpada. | 45
6 | Construction of Administrative / Institution Building of DIET, Narasinghpur. | 45
7 | Construction of Administrative 30 seated Hostel Building of DRC, Boudh | 22.5
8 | Construction of Administrative 30 seated Hostel Building of DRC, Jharsuguda. | 22.5
9 | Construction of Administrative 30 seated Hostel Building of DRC, Deogarh. | 22.5
10 | Construction of Administrative / Institution Building of DIET, Puri. | 75
| SCHOOL & MASS DEPARTMENT-TOTAL= | 442.5
TRIBAL AREA SUB- PLSN DEPARTMENT
1 | Construction of Building of DIET, Nawarangpur. | 45
2 | Construction of Building of DRC, Malkangiri. | 22.5
3 | Construction of Building of DRC, Nuapada. | 22.5
4 | Construction of Building of DRC, Baragarh. | 75
5 | Construction of Building of DRC, Gajapati, Parlakhemundi. | 75
6 | Construction of Building of DRC, Rayagada, Bisam Cuttack. | 75
7 | Construction of Building of DRC, Sonepur. | 22.5
8 | Construction of Building of CTE, Bhawanipatna. | 20.55
9 | Construction of Building of CTE, Rourkela. | 20.55
10 | Construction of Building of CTE, Baripada. | 20.55
| TRIBAL AREA SUB- PLSN DEPARTMENT-TOTAL= | 399.15

## Revenue_4216
STATEMENT SHOWING THE ALLOTMENT OF FUNDS IN RESPECT OF REVENUE & D.M. DEPTT. UNDER D.NO-7-4216-S.P.DURING THE YEAR 2010-11 (VOTE ON ACCOUNT)
(Rs. in Lakhs)
Sl. No. | Name of the Work | Head of Account with it's Sub-Head ----------------------- D. No-7-4216-Col- on- Housing- S.P.- S.S-01-GRB-106-GPA-during 2009-10 (Vote on Account) |  |  |  | A.A.Cost with No. & Date |  |  | Name of the (R&B) Division | Funds Allotted till 03/2010 |  | Allotment of Funds released under D. No-7-4216-Col- on- Housing- S.P.- S.S-01-GRB-106-GPA-during 2009-10 (Incl. P.C.) (Vote on Account) |  |  |  | Remarks
|  | General | 789-SCP | 796-TASP | Total | [6 empty] | General | 789-SCP | 796-TASP | Total
(1) | (2) | (3) |  |  |  | (4) |  |  | (5) | (6) |  | (7) |  |  |  | (8)
1 | Constn. of 3 nos. "E" type & 3 nos. "F" type qtrs. at Basudevpur. | 2 | 2 |  | 4 | A.D.M., Bhadrak Ltr. No-298 dt-22-05-08 | C.W. | 30.89 | Bhadrak | 07-08 | 8
[10 empty] | 08-09 | 18.87
[10 empty] | 09-10 | 4.02
[7 empty] | E.I. | 2.85 | G.E.D.-II | 08-09 | 2.85
[7 empty] | P.H. (I) | 4.28 | G.P.H.-I | 08-09 | 4.28
[7 empty] | P.H. (E) | 4.28 | G.P.H.-I | 09-10 | 0.28 | 2 | 2 |  | 4
|  | 2 | 2 | 0 | 4 |  | Total = | 42.3 |  |  | 38.3 | 2 | 2 | 0 | 4
2 | Constn. of 8 nos. "E" type & 4 nos. "F" type qtrs. at Bhadrak. | 10 |  |  | 10 | A.D.M., Bhadrak Ltr. No- 300 dt-22-05-08 | C.W. | 57.64 | Bhadrak | 08-09 | 57.64
[7 empty] | E.I. | 5.4 | G.E.D.-II | 08-09 | 1.5 | 3 |  |  | 3
[7 empty] | P.H. (I) | 8.11 | G.P.H.-I |  |  | 5 |  |  | 5
[7 empty] | P.H. (E) | 8.11 | G.P.H.-I |  |  | 2 |  |  | 2
|  | 10 | 0 | 0 | 10 |  | Total = | 79.26 |  |  | 59.14 | 10 | 0 | 0 | 10
3 | Constn. of 8 nos. "E" type & 8 nos. "F" type qtrs. at Baripada. |  |  | 4 | 4 | Collector & D.M., Mayurbhanj, Baripada Revised A.A. Ltr. No.513 dt-15-07-09 & Ltr. No379 dt-28-5-09 | C.W. | 74.47 | Mayurbhanj | 08-09 | 44
[10 empty] | 09-10 | 30.47
[7 empty] | E.I. | 7.37 | G.E.D.-II | 09-10 | 7.37
[7 empty] | P.H. (I) | 7.37 | G.P.H.-I | 09-10 | 7.37
[7 empty] | P.H. (E) | 11.05 | G.P.H.-I | 09-10 | 7.05 |  |  | 4 | 4
|  | 0 | 0 | 4 | 4 |  | Total = | 100.26 |  |  | 96.26 | 0 | 0 | 4 | 4
4 | Constn. of 6 nos. "E" type & 4 nos. "F" type qtrs. at Bolangir. (6 nos "E" type G/F, F/F & S/F) | 14.89 |  |  | 14.89 | Collector, Bolangir A.A.O. No- 08 dt-3-1-08 | C.W. | 53.69 | Bolangir | 08-09 | 20 | 7.6 |  |  | 7.6
[10 empty] | 09-10 | 24.09
[7 empty] | E.I. | 5.32 | G.E.D.-III | 09-10 | 2.5 | 2.82 |  |  | 2.82
[7 empty] | P.H. | 7.97 | G.P.H.-II | 09-10 | 3.5 | 4.47 |  |  | 4.47
|  | 14.89 | 0 | 0 | 14.89 |  | Total = | 66.98 |  |  | 50.09 | 14.89 | 0 | 0 | 14.89
5 | Constn. of 7 nos. "E" type qtrs. at Deogarh. | 9.34 |  |  | 9.34 | ADM, Deogarh A.A. No.6216 dt-20-10-2008 | C.W. | 56.4 | Sambalpur | 09-10 | 15 | 9.34 |  |  | 9.34 | NEW
[7 empty] | E.I. (I&E) | 6.77 | G.E.D.-III
[7 empty] | P.H(I& E) | 8.46 | G.P.H.-II
|  | 9.34 | 0 | 0 | 9.34 |  | Total = | 71.63 |  |  | 15 | 9.34 | 0 | 0 | 9.34
6 | Construction of resident and residential office of Collector, Cuttack | 6 |  |  | 6 | Collector, Cuttack Memo No. 2375 dt-27-04-2009 | C.W. | 48.1 | Cuttack | 08-09 | 15 | 6 |  |  | 6
[10 empty] | 09-10 | 15
[7 empty] | E.I. (I) | 4.76 | G.E.D.-II
[7 empty] | E.I. (E) | 0.5 | G.E.D.-II
[7 empty] | P.H. (I) | 4.76 | G.P.H.-I
[7 empty] | P.H. (E) | 4.76 | G.P.H.-I
|  | 6 | 0 | 0 | 6 |  | Total = | 62.88 |  |  | 30 | 6 | 0 | 0 | 6
7 | Constn. of 8 nos. (4 nos. "E" type M/S qtrs.) "E" type qtrs. at Jajpur. (Block "A" & Block "B") |  | 12 |  | 12 | Collelctor, Jajpur A.A. No-1749 dt-29-10-2008 | C.W. | 65.76 | Panikoili | 08-09 | 13.92 |  | 12 |  | 12
[10 empty] | 09-10 | 27.93
[7 empty] | E.I. | 5.58 | G.E.D.-II | 08-09 | 0.79
[7 empty] | P.H. (I) | 8.36 | G.P.H.-I
[7 empty] | P.H. (E) | 5.58 | G.P.H.-I
|  | 0 | 12 | 0 | 12 |  | Total = | 85.28 |  |  | 42.64 | 0 | 12 | 0 | 12
8 | Constn. of 4 nos. "E" type & 3 nos. "F" type qtrs. at Kamakhyanagar. | 8.55 |  |  | 8.55 | ADM, Dhenkanal Ltr. No-415 Dt. 09-04-08 | C.W. | 30.03 | Dhenkanal | 09-10 | 26.78 | 3.25 |  |  | 3.25
[7 empty] | E.I. | 2.95 | G.E.D.-II | 09-10 | 2 | 0.95 |  |  | 0.95
[7 empty] | P.H. (I) | 2.95 | G.P.H.-II | 09-10 | 2 | 0.95 |  |  | 0.95
[7 empty] | P.H. (E) | 4.4 | G.P.H.-II | 09-10 | 1 | 3.4 |  |  | 3.4
|  | 8.55 | 0 | 0 | 8.55 |  | Total = | 40.33 |  |  | 31.78 | 8.55 | 0 | 0 | 8.55
9 | Constn. of 9 nos. "F" type qtrs. at Gajapati. |  |  | 11 | 11 | Collector, Gajapati, Paralakhemundi Ltr. No.100 dt-6-1-09 | C.W. | 44.49 | Paralakhemundi | 09-10 | 30 |  |  | 11 | 11
[7 empty] | E.I. | 4.45 | G.E.D.-I
[7 empty] | P.H.(I) | 4.45 | G.P.H.-I
[7 empty] | P.H.(E) | 9.06 | G.P.H.-I
|  | 0 | 0 | 11 | 11 |  | Total = | 62.45 |  |  | 30 | 0 | 0 | 11 | 11
10 | Constn. of 15 nos. "E" type qtrs. at Nawarangapur. |  |  | 7 | 7 | A.A. accorded by Dy. Collelctor, Nawarangapur vide letter No-467 dt-06-08-2008 (Estimated cost Rs. 95.25 lakhs) | C.W. | 70.24 | Jeypore | 08-09 | 10.23
[10 empty] | 09-10 | 60.01
[7 empty] | E.I. | 7.06 | G.E.D.-IV | 09-10 | 7.06
[7 empty] | P.H. (I) | 7.06 | G.P.H.-II | 08-09 | 0.76
[10 empty] | 09-10 | 6.3
[7 empty] | P.H. (E) | 9.73 | G.P.H.-II | 09-10 | 2.73 |  |  | 7 | 7
|  | 0 | 0 | 7 | 7 |  | Total = | 94.09 |  |  | 87.09 | 0 | 0 | 7 | 7
11 | Construction of 2 nos. "E" type qtrs. in Purusottampur Tahasil. | 8.22 |  |  | 8.22 | Collector & D.M., Ganjam, Chhatrapur O.O No. 1452 dt. 09-11-09 | C.W. | 11.37 | Ganjam-II | 09-10 | 5 | 6.37 |  |  | 6.37
[7 empty] | E.I. | 1.14 | G.E.D.-I | 09-10 | 0.5 | 0.64 |  |  | 0.64
[7 empty] | P.H. | 1.71 | G.P.H.-I | 09-10 | 0.5 | 1.21 |  |  | 1.21
|  | 8.22 | 0 | 0 | 8.22 |  | Total = | 14.22 |  |  | 6 | 8.22 | 0 | 0 | 8.22
12 | Construction of residential building of Sub-Collector, Athamallik. | 2 | 3 |  | 5 | Collector, Angul O.O No. 606 dt. 25-04-07 | C.W. |  | Angul |  |  | 2 | 3 |  | 5 | NEW
[7 empty] | E.I. |  | G.E.D.-II
[7 empty] | P.H. |  | G.P.H.-II
|  | 2 | 3 | 0 | 5 |  | Total = | 15.4 |  |  | 0 | 2 | 3 | 0 | 5
Total (D. No-7-4216-S.P) = |  | 61 | 17 | 22 | 100 |  |  | 735.08 |  |  | 486.3 | 61 | 17 | 22 | 100

## Revenue_4059
STATEMENT SHOWING THE ALLOTMENT OF FUNDS IN RESPECT OF REVENUE & D.M. DEPTT. UNDER D.NO-7-4059-S.P. DURING THE YEAR 2010-11
(Rs. In Lakhs)
Sl. No. | Name of the Work | Head of Account with it's Sub-Head ----------------------- D. No-7-4059-COL- on- P.W.- S.P.- S.S.- 01-OB-051-Constn.during 2010-11 (Vote on Account) |  |  |  | A.A. cost with No. & Date |  |  | Name of (R&B) Division | Funds Alloted till 3 / 2010 (Incl PC) |  | Head of Account with it's Sub-Head ----------------------- Allotment of Funds released under D. No-7-4059-COL- on- P.W.- S.P.- S.S.- 01-OB-051-Constn.during 2010-11 (Incl. P.C.) (Vote on Account) |  |  |  | Remarks
|  | General | 789-SCP | 796-TASP | Total | [6 empty] | General | 789-SCP | 796-TASP | Total
(1) | (2) | (3) |  |  |  | (4) |  |  | (5) | (6) |  | (7) |  |  |  | (8)
1 | Construction of Collectorate Bldg. at Khurda. | 20 |  |  | 20 | RDC (CD) No.517, 02.07.07 | C.W. | 158.57 | Khurda | 07-08 | 33
[10 empty] | 08-09 | 50
[10 empty] | 09-10 | 75.57
[7 empty] | E.I.(I) | 15.86 | GED-I | 09-10 | 15.86
[7 empty] | P.H.(I) | 15.86 | GPH-I | 09-10 | 15.86
[7 empty] | P.H.(E) | 23.78 | GPH-I | 09-10 | 3.78 | 0 |  |  | 0
|  | 20 | 0 | 0 | 20 |  | Total= | 214.07 |  |  | 194.07 | 0 | 0 | 0 | 0
2 | Constn of Off. Bldg of Collectorate, Nayagarh. | 7 |  |  | 7 | RDC (CD) No- 519 / 2-7-07 | C.W. | 182.18 | Khurda | 07-08 | 50
[10 empty] | 08-09 | 50
[10 empty] | 09-10 | 82.18
[7 empty] | E.I.(I) | 9.02 | GED-I | 09-10 | 9.02
[7 empty] | P.H.(I) | 9.02 | GPH-I | 09-10 | 9.02
[7 empty] | P.H.(E) | 18.04 | GPH-I | 09-10 | 11.04 | 0 |  |  | 0
|  | 7 | 0 | 0 | 7 |  | Total= | 218.26 |  |  | 211.26 | 0 | 0 | 0 | 0
3 | Constn of Off. Bldg of Collectorate, Jharsuguda | 12.9 | 27.4 |  | 40.3 | R&DM Deptt. No-1725 / 11-1-08 | C.W. | 644.93 | Sambalpur | 09-10 | 62.62 | 12.9 | 27.4 |  | 40.3
[7 empty] | E.I.(I) | 41.15 | G.E.D.-III
[7 empty] | E.I.(E) | 33.37 | G.E.D.-III
[7 empty] | P.H.(I) | 17.18 | G.P.H.-II
[7 empty] | P.H.(E) | 7.76 | G.P.H.-II
|  | 12.9 | 27.4 | 0 | 40.3 |  | Total= | 744.39 |  |  | 62.62 | 12.9 | 27.4 | 0 | 40.3
4 | Construction of Collectorate Building at Sonepur (G.F.). | 25 |  |  | 25 | Member, Board of Revenue, Orissa, Cuttack letter No. 938 dt. 24-11-09 | C.W. | 223.97 | Bolangir | 09-10 | 10 | 25 |  |  | 25
[7 empty] | E.I. | 19.43 | GED-III
[7 empty] | P.H. (I) | 19.43 | GPH-II
[7 empty] | P.H. (E) | 19.42 | GPH-II
|  | 25 | 0 | 0 | 25 |  | Total | 282.25 |  |  | 10 | 25 | 0 | 0 | 25
5 | Construction of Collectorate building at Bhadrak (Balance work GF & Constn of FF) | 22 |  |  | 22 | Collector, Bhadrak Ltr. No. 498 dt. 28-09-2006 = 24.79 lakhs Balance work of GF & Constn. of FF = 36.30 lakhs. Total = 61.09 lakhs | C.W. |  | Bhadrak | 05-06 | 8 | 22 |  |  | 22
[10 empty] | 06-07 | 10
[10 empty] | 07-08 | 29.19
[10 empty] | 07-08 | 1.38
[10 empty] | 09-10 | 6.79
[7 empty] | E.I. |  | GED-II | 07-08 | 5.73
[7 empty] | PH(I& E) |  | GPH-I
|  | 22 | 0 | 0 | 22 |  | Total | 104.93 |  |  | 61.09 | 22 | 0 | 0 | 22
6 | Construction of Collectorate building, Malkanagiri. |  |  | 37.2 | 37.2 | R&DM Deptt. No-40208 / 18.09.08 | C.W. | 328.97 | Malkanagiri | 09-10 | 10 |  |  | 37.2 | 37.2
[7 empty] | E.I. (I) | 32.9 | G.E.D.-IV
[7 empty] | E.I. (E) | 17.57 | G.E.D.-IV
[7 empty] | P.H. (I) | 32.9 | G.P.H.-II
[7 empty] | P.H. (E) | 49.34 | G.P.H.-II
|  | 0 | 0 | 37.2 | 37.2 |  | Total | 461.68 |  |  | 10 | 0 | 0 | 37.2 | 37.2
7 | Construction of Collectorate building, Nuapada. | 15 |  |  | 15 | A.A. accorded by Member, Board of Revenue, Orissa, Cuttack on 03-12-09 | C.W. | 188.6 | Khariar |  |  | 15 |  |  | 15 | NEW
[7 empty] | E.I. (I) | 36.54 | G.E.D.-IV
[7 empty] | P.H. (I) | 18.27 | GPH-II
[7 empty] | P.H. (E) | 27.4 | GPH-II
|  | 15 | 0 | 0 | 15 |  | Total | 270.81 |  |  | 0 | 15 | 0 | 0 | 15
8 | Constn of Circuit House at Jharsuguda | 3.53 |  |  | 3.53 | Board of Rev, (O), Cuttack Memo No.1051, Dt.29.11.06 | C.W. | 108.13 | Sambalpur | 06-07 | 10 | 1.12 |  |  | 1.12
[10 empty] | 08-09 | 80
[10 empty] | 09-10 | 17.01
[7 empty] | E.I.(I) | 8.85 | G.E.D.-III | 08-09 | 8.5 | 0.35 |  |  | 0.35
[7 empty] | P.H.(I) | 8.37 | G.P.H.-II | 08-09 | 5
[10 empty] | 09-10 | 3.37
[7 empty] | P.H.(E) | 12.56 | G.P.H.-II | 08-09 | 6.5 | 2.06 |  |  | 2.06
[10 empty] | 09-10 | 4
|  | 3.53 | 0 | 0 | 3.53 |  | Total= | 137.91 |  |  | 134.38 | 3.53 | 0 | 0 | 3.53
9 | Construction of office building of Newly created Tahasil at Kashinagar in Gajapati District. |  |  | 19.89 | 19.89 | Revised A.A. accorded by Collector, Gajapati, Paralakhemundi Ltr. No. 8616 dt. 02-07-09 | C.W. | 59.65 | Paralakhemundi | 09-10 | 12 |  |  | 19.89 | 19.89
[7 empty] | E.I. | 5.96 | GED-I
[7 empty] | P.H. | 8.95 | GPH-I
|  | 0 | 0 | 19.89 | 19.89 |  | Total | 74.56 |  |  | 12 | 0 | 0 | 19.89 | 19.89
10 | Construction of Tahasil office Building, Belguntha. | 14 |  |  | 14 | Collector & D.M., Ganjam, Chhatrapur O.O. No.1162 dt.22.9.09 | C.W. | 66.42 | Bhanjanagar |  |  | 14 |  |  | 14
[7 empty] | E.I. | 5.43 | GED-I
[7 empty] | P.H. | 8.14 | GPH-I
|  | 14 | 0 | 0 | 14 |  | Total | 79.99 |  |  | 0 | 14 | 0 | 0 | 14
11 | Construction of office buildings of existing Tahasil at Athagarh. | 2.1 | 17.7 |  | 19.8 | A.D.M., Cuttack Order No.5336 dt.24-12-2008 | C.W. | 55.83 | Charbatia | 09-10 | 50.16 | 2.1 | 3.57 |  | 5.67
[7 empty] | E.I.(I) | 5.43 | GED-II | 09-10 | 2 |  | 3.43 |  | 3.43
[7 empty] | E.I.(E) | 0.12 | GED-II |  |  |  | 0.12 |  | 0.12
[7 empty] | P.H.(I) | 5.43 | GPH-I | 09-10 | 3 |  | 2.43 |  | 2.43
[7 empty] | P.H. (E) | 8.15 | GPH-I |  |  |  | 8.15 |  | 8.15
|  | 2.1 | 17.7 | 0 | 19.8 |  | Total | 74.96 |  |  | 55.16 | 2.1 | 17.7 | 0 | 19.8
12 | Construction of office buildings of existing Tahasil at Uditnagar, Rourkela. (G.F. & F.F.) |  |  | 4.11 | 4.11 | Collector, Sundargarh A.A. No.4005 dt-30.10.08 | C.W. | 52.49 | Rourkela | 08-09 | 15
[10 empty] | 09-10 | 37.49
[7 empty] | E.I. | 5.25 | GED-III | 09-10 | 5.25
[7 empty] | PH(I & E) | 13.11 | GPH-II | 09-10 | 9 |  |  | 4.11 | 4.11
|  | 0 | 0 | 4.11 | 4.11 |  | Total | 70.85 |  |  | 66.74 | 0 | 0 | 4.11 | 4.11
13 | Constn. of Tahasil office building at Polasara. | 20 |  |  | 20 | Collector & D.M., Ganjam, Chhatrapur O.O. No.1155 dt.22.9.09 | C.W. | 66.03 | Bhanjanagar | 09-10 | 25 | 20 |  |  | 20
[7 empty] | E.I. | 5.39 | G.E.D.-I
[7 empty] | P.H. (I) | 8.09 | G.P.H.-I
|  | 20 | 0 | 0 | 20 |  | Total | 79.51 |  |  | 25 | 20 | 0 | 0 | 20
14 | Constn. of Tahasil office building at Kabisuryanagar | 20 |  |  | 20 | Collector & D.M., Ganjam, Chhatrapur O.O. No.1155 dt.22.9.09 | C.W. | 66.18 | Bhanjanagar |  |  | 20 |  |  | 20
[7 empty] | E.I. | 5.4 | G.E.D.-I
[7 empty] | P.H. (I) | 8.11 | G.P.H.-I
|  | 20 | 0 | 0 | 20 |  | Total | 79.69 |  |  | 0 | 20 | 0 | 0 | 20
15 | Construction of Sub-Registrar office building at Banapur. | 4.75 | 3.67 |  | 8.42 | Collector & D.M., Khurda A.A. No.265 dt.12.2.09 | C.W. | 19.62 | Khurda | 08-09 | 18 | 1.62 |  |  | 1.62
[7 empty] | E.I. (I) | 1.94 | G.E.D.-I |  |  | 1.19 | 0.75 |  | 1.94
[7 empty] | P.H. (I) | 1.94 | G.P.H.-I |  |  | 1.94 |  |  | 1.94
[7 empty] | P.H.(E) | 2.92 | G.P.H.-I |  |  |  | 2.92 |  | 2.92
|  | 4.75 | 3.67 | 0 | 8.42 |  | Total | 26.42 |  |  | 18 | 4.75 | 3.67 | 0 | 8.42
16 | Construction of Sub-Registrar office building at Bamanghati in the District of Mayurbhanj. | 8.78 |  | 5 | 13.78 | A.D.M., Mayurbhanj Order No.09 dt.05.01.09 for R.O.B., Rairangapur. | C.W. | 19.28 | Rairangapur | 08-09 | 5 | 8.78 |  | 1.1 | 9.88
[7 empty] | E.I. | 1.72 | G.E.D.-II | 08-09 | 0.4 |  |  | 1.32 | 1.32
[7 empty] | P.H. (I) | 2.58 | G.P.H.-I |  |  |  |  | 2.58 | 2.58
|  | 8.78 | 0 | 5 | 13.78 |  | Total | 23.58 |  |  | 5.4 | 8.78 | 0 | 5 | 13.78
17 | Improvement of Sub-Collector Office Building at Koraput. |  |  | 8.9 | 8.9 | A.D.M., Koraput Ltr. No. 660 dt- 21-10-09 | C.W. |  | Koraput |  |  |  |  | 8.9 | 8.9 | NEW
[7 empty] | E.I. (I) |  | G.E.D.-IV
[7 empty] | E.I. (E) |  | G.E.D.-IV
[7 empty] | P.H. (I) |  | G.P.H.-II
[7 empty] | P.H.(E) |  | G.P.H.-II
|  | 0 | 0 | 8.9 | 8.9 |  | Total | 20 |  |  |  | 0 | 0 | 8.9 | 8.9
18 | Construction of the boundary wall of Sub-Collector-cum-Tahasil office building at Palalahara. | 2 | 2 |  | 4 | Collector, Angul Order No. 1786 dt-23-11-2006 | C.W. |  | Angul |  |  | 2 | 2 |  | 4
[7 empty] | E.I. (I) |  | G.E.D.-II
[7 empty] | E.I. (E) |  | G.E.D.-II
[7 empty] | P.H. (I) |  | G.P.H.-II
[7 empty] | P.H.(E) |  | G.P.H.-II
|  | 2 | 2 | 0 | 4 |  | Total | 11.58 |  |  |  | 2 | 2 | 0 | 4
19 | Construction of Circuit House, Sonepur. | 8.6 |  |  | 8.6 | Collector, Subarnapur Ltr. No-5251 dt- 19-5-10 | C.W. | 45.33 | Bolangir |  |  | 8.6 |  |  | 8.6 | NEW
[7 empty] | E.I. | 4.44 | G.E.D.-III
[7 empty] | P.H. | 4.44 | G.P.H.-II
|  | 8.6 | 0 | 0 | 8.6 |  | Total | 54.21 |  |  |  | 8.6 | 0 | 0 | 8.6
20 | Construction of Circuit House at Malkanagiri. | 10.4 |  | 12.1 | 22.5 | Collector, Malkanagiri Ltr. No. 622 dt. 10-6-10 | C.W. | 109.64 | Malkanagiri |  |  | 10.4 |  | 12.1 | 22.5 | NEW
[7 empty] | E.I. | 43.84 | G.E.D.-IV
[7 empty] | P.H. | 17.33 | G.P.H.-II
|  | 10.4 | 0 | 12.1 | 22.5 |  | Total | 170.81 |  |  |  | 10.4 | 0 | 12.1 | 22.5
21 | Construction of Circuit House at Berhampur. | 10.87 | 9 |  | 19.87 |  | C.W. |  | Ganjam-I | [5 empty] | 0 | NEW
[7 empty] | E.I. (I) |  | G.E.D.-I
[7 empty] | E.I. (E) |  | G.E.D.-I
[7 empty] | P.H. (I) |  | G.P.H.-I
[7 empty] | P.H.(E) |  | G.P.H.-I
|  | 10.87 | 9 | 0 | 19.87 |  | Total | 0 |  |  |  | 0 | 0 | 0 | 0
22 | Improvement of Revenue Rest Shed at Chandbali. | 11 |  |  | 11 | Collector, Bhadrak A.A. No- 97 dt-10-2-09 | C.W. | 19.18 | Bhadrak |  |  | 11 |  |  | 11 | NEW
[7 empty] | E.I. | 1.29 | G.E.D.-II
[7 empty] | P.H. | 1.94 | G.P.H.-I
|  | 11 | 0 | 0 | 11 |  | Total | 22.41 |  |  |  | 11 | 0 | 0 | 11
23 | Improvement of Circuit House at Khurda. | 8.1 |  |  | 8.1 | Collector, Khurda A.A. Order No. 1419 dt.19-7-2010 | C.W. | 19.89 | Khurda |  |  | 8.1 |  |  | 8.1
|  | 8.1 | 0 | 0 | 8.1 |  | Total | 19.89 |  |  |  | 8.1 | 0 | 0 | 8.1
24 | Improvement of Special Circuit House at Puri. | 3.4 | 4.6 |  | 8 | Collector, Puri Order No. 1715 dt-29-06-2010 | C.W. | 18.6 | Puri |  |  | 3.4 | 4.6 |  | 8 | NEW
|  | 3.4 | 4.6 | 0 | 8 |  | Total | 18.6 |  |  |  | 3.4 | 4.6 | 0 | 8
25 | Construction of Relief Go-down at Sambalpur. | 4.57 | 1.13 | 1.7 | 7.4 |  | C.W. |  | Sambalpur | [5 empty] | 0 | NEW
[7 empty] | E.I. (I) |  | G.E.D.-III
[7 empty] | E.I. (E) |  | G.E.D.-III
[7 empty] | P.H. (I) |  | G.P.H.-II
[7 empty] | P.H.(E) |  | G.P.H.-II
|  | 4.57 | 1.13 | 1.7 | 7.4 |  | Total | 0 |  |  |  | 0 | 0 | 0 | 0
26 | Construction of Tahasil office Building, Ganjam. | 10.1 |  |  | 10.1 | Collector & D.M., Ganjam O.O No- 223 dt- 29-1-2010 | C.W. | 66.52 | Ganjam-I |  |  | 10.1 |  |  | 10.1 | NEW
[7 empty] | E.I. | 6.15 | G.E.D.-I
[7 empty] | P.H. | 5.75 | G.P.H.-I
|  | 10.1 | 0 | 0 | 10.1 |  | Total | 78.42 |  |  |  | 10.1 | 0 | 0 | 10.1
Total (D-7-4059-SP) = |  | 244.1 | 65.5 | 88.9 | 398.5 |  |  | 3339.78 |  |  | 865.72 | 201.66 | 55.37 | 87.2 | 344.23
Facilitation Centre
1 | Construction of Facilitation centre at Sub-Collector office at Athagarh. | 1.42 |  |  | 1.42 | Dy. Collector, Cuttack Ltr. No.4 dt-2-1-09 | C.W. | 3.27 | Charbatia | 08-09 | 2.5 | 0.77 |  |  | 0.77
[7 empty] | EI | 0.24 | GED-II |  |  | 0.24 |  |  | 0.24
[7 empty] | PH | 0.41 | GPH-I |  |  | 0.41 |  |  | 0.41
|  | 1.42 | 0 | 0 | 1.42 |  | Total | 3.92 |  |  | 2.5 | 1.42 | 0 | 0 | 1.42
2 | Construction of Facilitation centre at Tahasil office at Athagarh. | 1.42 |  |  | 1.42 | Dy. Collector, Cuttack Ltr. No.4 dt-2-1-09 | C.W. | 3.27 | Charbatia | 08-09 | 2.5 | 0.77 |  |  | 0.77
[7 empty] | EI | 0.24 | GED-II |  |  | 0.24 |  |  | 0.24
[7 empty] | PH | 0.41 | GPH-I |  |  | 0.41 |  |  | 0.41
|  | 1.42 | 0 | 0 | 1.42 |  | Total | 3.92 |  |  | 2.5 | 1.42 | 0 | 0 | 1.42
3 | Construction of Facilitation centre at Tahasil office at Baramba. | 2.22 |  |  | 2.22 | Dy. Collector, cuttack Order No.470 dt-10-2-09 | C.W. | 3.5 | Charbatia | 08-09 | 2.5 | 1 |  |  | 1
[7 empty] | EI(I&E) | 0.35 | GED-II |  |  | 0.35 |  |  | 0.35
[7 empty] | PH(I) | 0.35 | GPH-I |  |  | 0.35 |  |  | 0.35
[7 empty] | PH(E) | 0.52 | GPH-I |  |  | 0.52 |  |  | 0.52
|  | 2.22 | 0 | 0 | 2.22 |  | Total | 4.72 |  |  | 2.5 | 2.22 | 0 | 0 | 2.22
4 | Construction of Facilitation centre at Tahasil office at Narsinghpur. | 2.39 |  |  | 2.39 | Dy. Collector, Cuttack Order No.7 dt-2-1-09 | C.W. | 3.63 | Charbatia | 08-09 | 2.5 | 1.13 |  |  | 1.13
[7 empty] | EI(I&E) | 0.36 | GED-II |  |  | 0.36 |  |  | 0.36
[7 empty] | PH(I) | 0.36 | GPH-I |  |  | 0.36 |  |  | 0.36
[7 empty] | PH(E) | 0.54 | GPH-I |  |  | 0.54 |  |  | 0.54
|  | 2.39 | 0 | 0 | 2.39 |  | Total | 4.89 |  |  | 2.5 | 2.39 | 0 | 0 | 2.39
Total (Charbatia) = |  | 7.45 | 0 | 0 | 7.45 |  |  | 17.45 |  |  | 10 | 7.45 | 0 | 0 | 7.45
5 | Construction of Facilitation centre at Collectorate, Balasore. | 0.31 |  |  | 0.31 | A.D.M., Balasore Ltr. No.34 dt.30-1-09 | C.W. | 2.81 | Balasore | 08-09 | 2.5 | 0.31 |  |  | 0.31
[7 empty] | E.I. | 0.41 | GED-II | 09-10 | 0.41
[7 empty] | P.H. | 0.53 | GPH-I | 09-10 | 0.53
|  | 0.31 | 0 | 0 | 0.31 |  | Total | 3.75 |  |  | 3.44 | 0.31 | 0 | 0 | 0.31
6 | Construction of Facilitation centre at Sub-Collector office at Balasore. | 0.44 |  |  | 0.44 | A.D.M., Balasore Ltr. No.34 dt.30-1-09 | C.W. | 2.94 | Balasore | 08-09 | 2.5 | 0.44 |  |  | 0.44
[7 empty] | E.I. | 0.41 | GED-II | 09-10 | 0.41
[7 empty] | P.H. | 0.53 | GPH-I | 09-10 | 0.53
|  | 0.44 | 0 | 0 | 0.44 |  | Total | 3.88 |  |  | 3.44 | 0.44 | 0 | 0 | 0.44
7 | Construction of Facilitation centre at Tahasil office at Balasore. | 0.31 |  |  | 0.31 | A.D.M., Balasore Ltr. No.34 dt.30-1-09 | C.W. | 2.81 | Balasore | 08-09 | 2.5 | 0.31 |  |  | 0.31
[7 empty] | E.I. | 0.41 | GED-II | 09-10 | 0.41
[7 empty] | P.H. | 0.53 | GPH-I | 09-10 | 0.53
|  | 0.31 | 0 | 0 | 0.31 |  | Total | 3.75 |  |  | 3.44 | 0.31 | 0 | 0 | 0.31
8 | Construction of Facilitation centre at Tahasil office at Basta. | 0.74 |  |  | 0.74 | A.D.M., Balasore Ltr. No.34 dt.30-1-09 | C.W. | 3.24 | Balasore | 08-09 | 2.5 | 0.74 |  |  | 0.74
[7 empty] | E.I. | 0.41 | GED-II | 09-10 | 0.41
[7 empty] | P.H. | 0.53 | GPH-I | 09-10 | 0.53
|  | 0.74 | 0 | 0 | 0.74 |  | Total | 4.18 |  |  | 3.44 | 0.74 | 0 | 0 | 0.74
9 | Construction of Facilitation centre at Tahasil office at Soro. | 0.43 |  |  | 0.43 | A.D.M., Balasore Ltr. No.34 dt.30-1-09 | C.W. | 2.93 | Balasore | 08-09 | 2.5 | 0.43 |  |  | 0.43
[7 empty] | E.I. | 0.41 | GED-II | 09-10 | 0.41
[7 empty] | P.H. | 0.53 | GPH-I | 09-10 | 0.53
|  | 0.43 | 0 | 0 | 0.43 |  | Total | 3.87 |  |  | 3.44 | 0.43 | 0 | 0 | 0.43
10 | Construction of Facilitation centre at Sub-Collector office at Nilagiri | 0.45 |  |  | 0.45 | A.D.M., Balasore Ltr. No.34 dt.30-1-09 | C.W. | 2.95 | Balasore | 08-09 | 2.5 | 0.45 |  |  | 0.45
[7 empty] | E.I. | 0.41 | GED-II | 09-10 | 0.41
[7 empty] | P.H. | 0.53 | GPH-I | 09-10 | 0.53
|  | 0.45 | 0 | 0 | 0.45 |  | Total | 3.89 |  |  | 3.44 | 0.45 | 0 | 0 | 0.45
11 | Construction of Facilitation centre at Tahasil office at Nilagiri | 0.45 |  |  | 0.45 | A.D.M., Balasore Ltr. No.34 dt.30-1-09 | C.W. | 2.95 | Balasore | 08-09 | 2.5 | 0.45 |  |  | 0.45
[7 empty] | E.I. | 0.41 | GED-II | 09-10 | 0.41
[7 empty] | P.H. | 0.53 | GPH-I | 09-10 | 0.53
|  | 0.45 | 0 | 0 | 0.45 |  | Total | 3.89 |  |  | 3.44 | 0.45 | 0 | 0 | 0.45
12 | Construction of Facilitation centre at Tahasil office at Jaleswar. | 3.41 |  |  | 3.41 | Dy. Collector, (Nizarat), Balasore No. 233 dt 11-05-09 | C.W. | 3.28 | Balasore |  |  | 3.28 |  |  | 3.28
[7 empty] | E.I. | 0.41 | GED-II |  |  | 0.13 |  |  | 0.13
[7 empty] | P.H. | 0.53 | GPH-I
|  | 3.41 | 0 | 0 | 3.41 |  | Total | 4.22 |  |  |  | 3.41 | 0 | 0 | 3.41
| Total (Balasore) = | 6.54 | 0 | 0 | 6.54 |  |  | 31.43 |  |  | 24.08 | 6.54 | 0 | 0 | 6.54
13 | Construction of Facilitation centre at Tahasil office at Pipili. | 0.6 |  |  | 0.6 | A.A. Accorded as reported by E.E., BBSR No-II vide his Ltr. No.234 dt.19.1.09 | C.W. | 3.1 | BBSR-II | 08-09 | 2.5 | 0.6 |  |  | 0.6
[7 empty] | E.I. | 0.41 | GED-I | 09-10 | 0.41
[7 empty] | P.H. | 0.47 | GPH-I | 09-10 | 0.47
|  | 0.6 | 0 | 0 | 0.6 |  | Total | 3.98 |  |  | 3.38 | 0.6 | 0 | 0 | 0.6
14 | Construction of Facilitation centre at Sub-Collector office at Bhubaneswar. | 0.63 |  |  | 0.63 | Collector & D.M., Khurda Ltr. No.25 dt. 5-1-09 | C.W. | 3.13 | BBSR-II | 08-09 | 2.5 | 0.63 |  |  | 0.63
[7 empty] | E.I. | 0.41 | G.E.D.-I | 09-10 | 0.41
[7 empty] | P.H. | 0.29 | G.P.H.-I | 09-10 | 0.29
|  | 0.63 | 0 | 0 | 0.63 |  | Total | 3.83 |  |  | 3.2 | 0.63 | 0 | 0 | 0.63
15 | Construction of Facilitation centre at Tahasil office at Bhubaneswar. | 0.63 |  |  | 0.63 | Collector & D.M., Khurda Ltr. No.29 dt.5-1-09 | C.W. | 3.13 | BBSR-II | 08-09 | 2.5 | 0.63 |  |  | 0.63
[7 empty] | E.I. | 0.41 | G.E.D.-I | 09-10 | 0.41
[7 empty] | P.H. | 0.29 | G.P.H.-I | 09-10 | 0.29
|  | 0.63 | 0 | 0 | 0.63 |  | Total | 3.83 |  |  | 3.2 | 0.63 | 0 | 0 | 0.63
Total (BBSR-II) = |  | 1.86 | 0 | 0 | 1.86 |  |  | 11.64 |  |  | 9.78 | 1.86 | 0 | 0 | 1.86
16 | Construction of Facilitation centre at Tahasil office, Banapur. | 0.08 |  |  | 0.08 | Collector & D.M., Khurda Ltr. No.2152 dt. 23-12-08 | C.W. | 2.58 | Khurda | 08-09 | 2.5 | 0.08 |  |  | 0.08
[7 empty] | E.I. | 0.09 | G.E.D.-I | 09-10 | 0.09
[7 empty] | P.H. | 0.09 | G.P.H.-I | 09-10 | 0.09
|  | 0.08 | 0 | 0 | 0.08 |  | Total | 2.76 |  |  | 2.68 | 0.08 | 0 | 0 | 0.08
| Total (Khurda) = | 0.08 | 0 | 0 | 0.08 |  |  | 2.76 | 0 | 0 | 2.68 | 0.08 | 0 | 0 | 0.08
17 | Construction of Facilitation centre at Collectorate, Angul | 1.27 |  |  | 1.27 | Collector, Angul Ltr. No- 1692 dt-17-09-2008 | C.W. | 3.77 | Angul | 08-09 | 2.5 | 1.27 |  |  | 1.27
[7 empty] | E.I. | 0.38 | GED-II | 09-10 | 0.38
[7 empty] | P.H. | 0.38 | GPH-II | 09-10 | 0.38
|  | 1.27 | 0 | 0 | 1.27 |  | Total | 4.53 |  |  | 3.26 | 1.27 | 0 | 0 | 1.27
18 | Construction of Facilitation centre at Sub-Collector office at Angul | 1.27 |  |  | 1.27 | Collector, Angul Ltr. No- 1687 dt-15-09-2008 | C.W. | 3.77 | Angul | 08-09 | 2.5 | 1.27 |  |  | 1.27
[7 empty] | E.I. | 0.38 | GED-II | 09-10 | 0.38
[7 empty] | P.H. | 0.38 | GPH-II | 09-10 | 0.38
|  | 1.27 | 0 | 0 | 1.27 |  | Total | 4.53 |  |  | 3.26 | 1.27 | 0 | 0 | 1.27
19 | Construction of Facilitation centre at Tahasil office at Angul | 0.88 |  |  | 0.88 | Collector, Angul Ltr. No- 1677 dt-15-09-2008 | C.W. | 3.77 | Angul | 08-09 | 2.89 | 0.88 |  |  | 0.88
[7 empty] | E.I. | 0.38 | GED-II | 09-10 | 0.38
[7 empty] | P.H. | 0.38 | GPH-II | 08-09 | 0.31
[10 empty] | 09-10 | 0.07
|  | 0.88 | 0 | 0 | 0.88 |  | Total | 4.53 |  |  | 3.65 | 0.88 | 0 | 0 | 0.88
20 | Construction of Facilitation centre at Sub-Collector office at Talcher | 0.66 |  |  | 0.66 | Collector, Angul Ltr. No- 1697 dt-15-09-2008 | C.W. | 3.76 | Angul | 08-09 | 3.1 | 0.66 |  |  | 0.66
[7 empty] | E.I. | 0.37 | GED-II | 09-10 | 0.37
[7 empty] | P.H. | 0.37 | GPH-II | 09-10 | 0.37
|  | 0.66 | 0 | 0 | 0.66 |  | Total | 4.5 |  |  | 3.84 | 0.66 | 0 | 0 | 0.66
21 | Construction of Facilitation centre at Tahasil office at Talcher | 0.66 |  |  | 0.66 | Collector, Angul Ltr. No- 1692 dt-15-09-2008 | C.W. | 3.76 | Angul | 08-09 | 3.1 | 0.66 |  |  | 0.66
[7 empty] | E.I. | 0.37 | GED-II | 09-10 | 0.37
[7 empty] | P.H. | 0.37 | GPH-II | 09-10 | 0.37
|  | 0.66 | 0 | 0 | 0.66 |  | Total | 4.5 |  |  | 3.84 | 0.66 | 0 | 0 | 0.66
22 | Construction of Facilitation centre at Sub-Collector office at Athamallik |  |  | 1.17 | 1.17 | Collector, Angul Ltr. No- 1677 dt-15-09-2008 | C.W. | 3.67 | Angul | 08-09 | 2.5 |  |  | 1.17 | 1.17
[7 empty] | E.I. | 0.37 | GED-II | 09-10 | 0.37
[7 empty] | P.H. | 0.37 | GPH-II | 09-10 | 0.37
|  | 0 | 0 | 1.17 | 1.17 |  | Total | 4.41 |  |  | 3.24 | 0 | 0 | 1.17 | 1.17
23 | Construction of Facilitation centre at Tahasil office at Athamallik |  |  | 1.17 | 1.17 | Collector, Angul Ltr. No- 1677 dt-15-09-2008 | C.W. | 3.67 | Angul | 08-09 | 2.5 |  |  | 1.17 | 1.17
[7 empty] | E.I. | 0.37 | GED-II | 09-10 | 0.37
[7 empty] | P.H. | 0.37 | GPH-II | 09-10 | 0.37
|  | 0 | 0 | 1.17 | 1.17 |  | Total | 4.41 |  |  | 3.24 | 0 | 0 | 1.17 | 1.17
24 | Construction of Facilitation centre at Sub-Collector office at Pallahara |  |  | 0.89 | 0.89 | Collector, Angul Ltr. No- 1717 dt-15-09-2008 | C.W. | 3.79 | Angul | 08-09 | 2.9 |  |  | 0.89 | 0.89
[7 empty] | E.I. | 0.38 | GED-II | 08-09 | 0.37
[10 empty] | 09-10 | 0.01
[7 empty] | P.H. | 0.38 | GPH-II | 09-10 | 0.38
|  | 0 | 0 | 0.89 | 0.89 |  | Total | 4.55 |  |  | 3.66 | 0 | 0 | 0.89 | 0.89
25 | Construction of Facilitation centre at Tahasil office at Pallahara. |  |  | 0.89 | 0.89 | Collector, Angul Ltr. No- 1712 dt-15-09-2008 | C.W. | 3.79 | Angul | 08-09 | 2.9 |  |  | 0.89 | 0.89
[7 empty] | E.I. | 0.38 | GED-II | 08-09 | 0.31
[10 empty] | 09-10 | 0.07
[7 empty] | P.H. | 0.38 | GPH-II | 09-10 | 0.38
|  | 0 | 0 | 0.89 | 0.89 |  | Total | 4.55 |  |  | 3.66 | 0 | 0 | 0.89 | 0.89
| Total (Angul) = | 4.74 | 0 | 4.12 | 8.86 |  |  | 40.51 |  |  | 31.65 | 4.74 | 0 | 4.12 | 8.86
26 | Construction of Facilitation centre at Collectorate, Baragarh | 0.59 |  |  | 0.59 | No. -3811 dt- 2-8-08 Addressed to Collector, Baragarh. |  | 3.087 | Baragarh | 08-09 | 2.5 | 0.59 |  |  | 0.59
27 | Construction of Facilitation centre at Sub-Collector office at Baragarh | 0.59 |  |  | 0.59 |  |  | 3.087 | Baragarh | 08-09 | 2.5 | 0.59 |  |  | 0.59
28 | Construction of Facilitation centre at Tahasil office at Baragarh | 0.59 |  |  | 0.59 |  |  | 3.087 | Baragarh | 08-09 | 2.5 | 0.59 |  |  | 0.59
29 | Construction of Facilitation centre at Tahasil office at Barapali |  | 0.53 |  | 0.53 |  |  | 3.032 | Baragarh | 08-09 | 2.5 |  | 0.53 |  | 0.53
30 | Construction of Facilitation centre at Sub-Collector office at Padmapur |  | 0.52 |  | 0.52 |  |  | 3.022 | Baragarh | 08-09 | 2.5 |  | 0.52 |  | 0.52
31 | Construction of Facilitation centre at Tahasil office at Padmapur |  | 0.52 |  | 0.52 |  |  | 3.022 | Baragarh | 08-09 | 2.5 |  | 0.52 |  | 0.52
32 | Construction of Facilitation centre at Tahasil office at Sohela |  | 0.59 |  | 0.59 |  |  | 3.095 | Baragarh | 08-09 | 2.5 |  | 0.59 |  | 0.59
Total (Baragarh) = |  | 1.77 | 2.16 | 0 | 3.93 |  |  | 21.432 |  |  | 17.5 | 1.77 | 2.16 | 0 | 3.93
33 | Construction of Facilitation centre at Sub-Collector office at Panposh. | 0.73 |  |  | 0.73 | Estimate submitted to the Collector, Sundargarh for A.A. |  | 6.465 | Rourkela | 08-09 | 2.5 | 0.73 |  |  | 0.73
34 | Construction of Facilitation centre at Tahasil office at Panposh. | 0.73 |  |  | 0.73 |  |  |  | Rourkela | 08-09 | 2.5 | 0.73 |  |  | 0.73
35 | Construction of Facilitation centre at Tahasil office at Biramitrapur. | 2.22 |  |  | 2.22 |  |  | 4.72 | Rourkela | 08-09 | 2.5 | 2.22 |  |  | 2.22
36 | Construction of Facilitation centre at Tahasil office at Rourkela. | 1.78 |  | 2.04 | 3.82 |  |  | 6.32 | Rourkela | 08-09 | 2.5 | 1.78 |  | 2.04 | 3.82
37 | Construction of Facilitation centre at Sub-Collector office at Bonai |  | 0.72 | 1.61 | 2.33 |  |  | 4.825 | Rourkela | 08-09 | 2.5 |  | 0.72 | 1.61 | 2.33
38 | Construction of Facilitation centre at Tahasil office at Bonai |  |  | 2.33 | 2.33 |  |  | 4.825 | Rourkela | 08-09 | 2.5 |  |  | 2.33 | 2.33
Total (Rourkela) = |  | 5.46 | 0.72 | 5.98 | 12.16 |  |  | 27.155 |  |  | 15 | 5.46 | 0.72 | 5.98 | 12.16
39 | Construction of Facilitation centre at Sub-Collector office at Paralakhemundi |  | 1 |  | 1 | District Development Officer, Gajapati, Paralakhemundi A.A No.11193 dt.10.11.08 |  | 2.5 | Paralakhemundi | 08-09 | 1.5 |  | 1 |  | 1
40 | Construction of Facilitation centre at Tahasil office at Paralakhemundi |  | 1 |  | 1 |  |  | 2.5 | Paralakhemundi | 08-09 | 1.5 |  | 1 |  | 1
Total (P.Khemundi)= |  | 0 | 2 | 0 | 2 |  |  | 5 |  |  | 3 | 0 | 2 | 0 | 2
41 | Construction of Facilitation centre at Sub-Collector office at Jeypore |  | 0.15 |  | 0.15 | Collector, Koraput Ltr. No-209 dt-12-08-2008 | C.W. | 2.65 | Jeypore | 08-09 | 2.5 |  | 0.15 |  | 0.15
[7 empty] | E.I. | 0.27 | GED-IV | 09-10 | 0.27
[7 empty] | P.H. | 0.39 | GPH-II | 09-10 | 0.39
|  | 0 | 0.15 | 0 | 0.15 |  | Total | 3.31 |  |  | 3.16 | 0 | 0.15 | 0 | 0.15
42 | Construction of Facilitation centre at Tahasil office at Jeypore |  | 0.15 |  | 0.15 | Collector, Koraput Ltr. No-209 dt-12-08-2008 | C.W. | 2.65 | Jeypore | 08-09 | 2.5 |  | 0.15 |  | 0.15
[7 empty] | E.I. | 0.27 | GED-IV | 09-10 | 0.27
[7 empty] | P.H. | 0.39 | GPH-II | 09-10 | 0.39
|  | 0 | 0.15 | 0 | 0.15 |  | Total | 3.31 |  |  | 3.16 | 0 | 0.15 | 0 | 0.15
43 | Construction of Facilitation centre at Tahasil office at Kotpad |  | 0.16 |  | 0.16 | Collector, Koraput Ltr. No-209 dt-12-08-2008 | C.W. | 2.66 | Jeypore | 08-09 | 2.5 |  | 0.16 |  | 0.16
[7 empty] | E.I. | 0.27 | GED-IV | 09-10 | 0.27
[7 empty] | P.H. | 0.39 | GPH-II | 09-10 | 0.39
|  | 0 | 0.16 | 0 | 0.16 |  | Total | 3.32 |  |  | 3.16 | 0 | 0.16 | 0 | 0.16
44 | Construction of Facilitation centre at Collectorate, Nawarangapur |  | 0.14 |  | 0.14 | Collector, Nawarangapur Ltr. No-467 dt-06-08-2008 | C.W. | 2.64 | Jeypore | 08-09 | 2.5 |  | 0.14 |  | 0.14
[7 empty] | E.I. | 0.26 | GED-IV | 09-10 | 0.26
[7 empty] | P.H. | 0.4 | GPH-II | 09-10 | 0.4
|  | 0 | 0.14 | 0 | 0.14 |  | Total | 3.3 |  |  | 3.16 | 0 | 0.14 | 0 | 0.14
45 | Construction of Facilitation centre at Sub-Collector office at Nawarangapur |  | 0.14 |  | 0.14 | Collector, Nawarangapur Ltr. No-467 dt-06-08-2008 | C.W. | 2.64 | Jeypore | 08-09 | 2.5 |  | 0.14 |  | 0.14
[7 empty] | E.I. | 0.26 | GED-IV | 09-10 | 0.26
[7 empty] | P.H. | 0.4 | GPH-II | 09-10 | 0.4
|  | 0 | 0.14 | 0 | 0.14 |  | Total | 3.3 |  |  | 3.16 | 0 | 0.14 | 0 | 0.14
46 | Construction of Facilitation centre at Tahasil office at Nawarangapur |  | 0.14 |  | 0.14 | Collector, Nawarangapur Ltr. No-467 dt-06-08-2008 | C.W. | 2.64 | Jeypore | 08-09 | 2.5 |  | 0.14 |  | 0.14
[7 empty] | E.I. | 0.26 | GED-IV | 09-10 | 0.26
[7 empty] | P.H. | 0.4 | GPH-II | 09-10 | 0.4
|  | 0 | 0.14 | 0 | 0.14 |  | Total | 3.3 |  |  | 3.16 | 0 | 0.14 | 0 | 0.14
47 | Construction of Facilitation centre at Tahasil office at Umerkote |  | 0.27 |  | 0.27 | Collector, Nawarangapur Ltr. No-467 dt-06-08-2008 | C.W. | 2.77 | Jeypore | 08-09 | 2.5 |  | 0.27 |  | 0.27
[7 empty] | E.I. | 0.28 | GED-IV | 09-10 | 0.28
[7 empty] | P.H. | 0.41 | GPH-II | 09-10 | 0.41
|  | 0 | 0.27 | 0 | 0.27 |  | Total | 3.46 |  |  | 3.19 | 0 | 0.27 | 0 | 0.27
| Total (Jeypore) = | 0 | 1.15 | 0 | 1.15 |  |  | 23.3 |  |  | 22.15 | 0 | 1.15 | 0 | 1.15
48 | Construction of Facilitation centre at Collectorate, Malkanagiri |  | 0.49 |  | 0.49 | No-589 dt-20-10-2008 of Collector, Malkanagiri (As reported by Executive Engineer, Malkanagiri vide Division No-2922 dt-16-10-08) | C.W. | 2.99 | Malkanagiri | 08-09 | 2.5 |  | 0.49 |  | 0.49
[7 empty] | E.I. | 0.29 | GED-IV | 09-10 | 0.29
[7 empty] | P.H. | 0.37 | GPH-II | 09-10 | 0.37
|  | 0 | 0.49 | 0 | 0.49 |  | Total | 3.65 |  |  | 3.16 | 0 | 0.49 | 0 | 0.49
49 | Construction of Facilitation centre at Sub-Collector office at Malkanagiri |  | 0.49 |  | 0.49 |  | C.W. | 2.99 | Malkanagiri | 08-09 | 2.5 |  | 0.49 |  | 0.49
[7 empty] | E.I. | 0.29 | GED-IV | 09-10 | 0.29
[7 empty] | P.H. | 0.37 | GPH-II | 09-10 | 0.37
|  | 0 | 0.49 | 0 | 0.49 |  | Total | 3.65 |  |  | 3.16 | 0 | 0.49 | 0 | 0.49
50 | Construction of Facilitation centre at Tahasil office at Malkanagiri |  | 0.49 |  | 0.49 |  | C.W. | 2.99 | Malkanagiri | 08-09 | 2.5 |  | 0.49 |  | 0.49
[7 empty] | E.I. | 0.29 | GED-IV | 09-10 | 0.29
[7 empty] | P.H. | 0.37 | GPH-II | 09-10 | 0.37
|  | 0 | 0.49 | 0 | 0.49 |  | Total | 3.65 |  |  | 3.16 | 0 | 0.49 | 0 | 0.49
| Total (Malkanagiri)= | 0 | 1.47 | 0 | 1.47 |  |  | 10.95 |  |  | 9.48 | 0 | 1.47 | 0 | 1.47
Total (FC 1st Ph.) = |  | 27.9 | 7.5 | 10.1 | 45.5 |  |  | 191.627 |  |  | 145.32 | 27.9 | 7.5 | 10.1 | 45.5
1 | Construction of Facilitation centre at Collectorate, Kendrapara. | 1.46 |  |  | 1.46 | Collector, Kendrapara A.A. No. 15909 dt-04-10-08 | C.W. | 3.3 | Kendrapara | 08-09 | 2.5 | 0.8 |  |  | 0.8
[7 empty] | E.I. | 0.33 | G.E.D-II |  |  | 0.33 |  |  | 0.33
[7 empty] | P.H. | 0.33 | G.P.H-I |  |  | 0.33 |  |  | 0.33
|  | 1.46 |  |  | 1.46 |  | Total = | 3.96 |  |  | 2.5 | 1.46 |  |  | 1.46
2 | Construction of Facilitation centre at Sub-Collector office at Kendrapara. | 1.44 |  |  | 1.44 | Collector, Kendrapara A.A. No. 15909 dt-04-10-08 | C.W. | 3.28 | Kendrapara | 08-09 | 2.5 | 0.78 |  |  | 0.78
[7 empty] | E.I. | 0.33 | G.E.D-II |  |  | 0.33 |  |  | 0.33
[7 empty] | P.H. | 0.33 | G.P.H-I |  |  | 0.33 |  |  | 0.33
|  | 1.44 |  |  | 1.44 |  | Total = | 3.94 |  |  | 2.5 | 1.44 |  |  | 1.44
3 | Construction of Facilitation centre at Tahasil office at Aul. | 0.78 |  |  | 0.78 | Collector, Kendrapara A.A. No. 15909 dt-04-10-08 | C.W. | 3 | Kendrapara | 08-09 | 2.5 | 0.5 |  |  | 0.5
[7 empty] | E.I. | 0.28 | G.E.D-II |  |  | 0.28 |  |  | 0.28
[7 empty] | P.H. | 0.43 | G.P.H-I | 09-10 | 0.5 |  |  |  | 0
|  | 0.78 |  |  | 0.78 |  | Total = | 3.71 |  |  | 3 | 0.78 |  |  | 0.78
4 | Construction of Facilitation centre at Tahasil office at Kanika. | 0.83 |  |  | 0.83 | Collector, Kendrapara A.A. No. 15909 dt-04-10-08 | C.W. | 3.05 | Kendrapara | 08-09 | 2.5 | 0.55 |  |  | 0.55
[7 empty] | E.I. | 0.28 | G.E.D-II |  |  | 0.28 |  |  | 0.28
[7 empty] | P.H. | 0.43 | G.P.H-I | 09-10 | 0.5 |  |  |  | 0
|  | 0.83 |  |  | 0.83 |  | Total = | 3.76 |  |  | 3 | 0.83 |  |  | 0.83
5 | Construction of Facilitation centre at Tahasil office at Kendrapara. | 1.33 |  |  | 1.33 | Collector, Kendrapara A.A. No. 15909 dt-04-10-08 | C.W. | 3.19 | Kendrapara | 08-09 | 2.5 | 0.69 |  |  | 0.69
[7 empty] | E.I. | 0.32 | G.E.D-II |  |  | 0.32 |  |  | 0.32
[7 empty] | P.H. | 0.32 | G.P.H-I |  |  | 0.32 |  |  | 0.32
|  | 1.33 |  |  | 1.33 |  | Total = | 3.83 |  |  | 2.5 | 1.33 |  |  | 1.33
6 | Construction of Facilitation centre at Tahasil office at Pattamundai. | 1.14 |  |  | 1.14 | Collector, Kendrapara A.A. No. 15909 dt-04-10-08 | C.W. | 2.91 | Kendrapara | 08-09 | 2.5 | 0.41 |  |  | 0.41
[7 empty] | E.I. | 0.29 | G.E.D-II |  |  | 0.29 |  |  | 0.29
[7 empty] | P.H. | 0.44 | G.P.H-I |  |  | 0.44 |  |  | 0.44
|  | 1.14 |  |  | 1.14 |  | Total = | 3.64 |  |  | 2.5 | 1.14 |  |  | 1.14
Total (Kendrapara) = |  | 6.98 |  |  | 6.98 |  |  | 22.84 |  |  | 16 | 6.98 |  |  | 6.98
7 | Construction of Facilitation centre at Tahasil office at Jaleswar. | 0.81 |  |  | 0.81 | Dy. Collector (Nizarat), Balasore Ltr. No. 233 dt-11-5-09 | C.W. | 3.28 | Balasore | 10-11 | 3.28 | 0 |  |  | 0
[7 empty] | E.I. | 0.41 | G.E.D-II | 10-11 | 0.13 | 0.28 |  |  | 0.28
[7 empty] | P.H. | 0.53 | G.P.H-I |  |  | 0.53 |  |  | 0.53
|  | 0.81 |  |  | 0.81 |  | Total = | 4.22 |  |  | 3.41 | 0.81 |  |  | 0.81
| Total (Balasore) = | 0.81 |  |  | 0.81 |  |  | 4.22 |  |  | 3.41 | 0.81 |  |  | 0.81
8 | Construction of Facilitation centre at Collectorate, Bhadrak. | 1.39 |  |  | 1.39 | A.D.M., Bhadrak Ltr. No. 677 dt-27-10-08 | C.W. | 3.03 | Bhadrak | 08-09 | 2.5 | 0.53 |  |  | 0.53
[7 empty] | E.I. | 0.41 | G.E.D-II |  |  | 0.41 |  |  | 0.41
[7 empty] | P.H. | 0.45 | G.P.H-I |  |  | 0.45 |  |  | 0.45
|  | 1.39 |  |  | 1.39 |  | Total = | 3.89 |  |  | 2.5 | 1.39 |  |  | 1.39
9 | Construction of Facilitation centre at Sub-Collector office at Bhadrak. | 1.39 |  |  | 1.39 | A.D.M., Bhadrak Ltr. No. 677 dt-27-10-08 | C.W. | 3.03 | Bhadrak | 08-09 | 2.5 | 0.53 |  |  | 0.53
[7 empty] | E.I. | 0.41 | G.E.D-II |  |  | 0.41 |  |  | 0.41
[7 empty] | P.H. | 0.45 | G.P.H-I |  |  | 0.45 |  |  | 0.45
|  | 1.39 |  |  | 1.39 |  | Total = | 3.89 |  |  | 2.5 | 1.39 |  |  | 1.39
10 | Construction of Facilitation centre at Tahasil office at Bhadrak. | 1.39 |  |  | 1.39 | A.D.M., Bhadrak Ltr. No. 677 dt-27-10-08 | C.W. | 3.03 | Bhadrak | 08-09 | 2.5 | 0.53 |  |  | 0.53
[7 empty] | E.I. | 0.41 | G.E.D-II |  |  | 0.41 |  |  | 0.41
[7 empty] | P.H. | 0.45 | G.P.H-I |  |  | 0.45 |  |  | 0.45
|  | 1.39 |  |  | 1.39 |  | Total = | 3.89 |  |  | 2.5 | 1.39 |  |  | 1.39
11 | Construction of Facilitation centre at Tahasil office at Chandabali. | 2.09 |  |  | 2.09 | A.D.M., Bhadrak Ltr. No. 677 dt-27-10-08 | C.W. | 3.73 | Bhadrak | 08-09 | 2.5 | 1.23 |  |  | 1.23
[7 empty] | E.I. | 0.41 | G.E.D-II |  |  | 0.41 |  |  | 0.41
[7 empty] | P.H. | 0.45 | G.P.H-I |  |  | 0.45 |  |  | 0.45
|  | 2.09 |  |  | 2.09 |  | Total = | 4.59 |  |  | 2.5 | 2.09 |  |  | 2.09
12 | Construction of Facilitation centre at Tahasil office at Basudevpur. | 1.99 |  |  | 1.99 | A.D.M., Bhadrak Ltr. No. 677 dt-27-10-08 | C.W. | 3.63 | Bhadrak | 08-09 | 2.5 | 1.13 |  |  | 1.13
[7 empty] | E.I. | 0.41 | G.E.D-II |  |  | 0.41 |  |  | 0.41
[7 empty] | P.H. | 0.45 | G.P.H-I |  |  | 0.45 |  |  | 0.45
|  | 1.99 |  |  | 1.99 |  | Total = | 4.49 |  |  | 2.5 | 1.99 |  |  | 1.99
| Total (Bhadrak) = | 8.25 |  |  | 8.25 |  |  | 20.75 |  |  | 12.5 | 8.25 |  |  | 8.25
13 | Construction of Facilitation centre at Tahasil office at Jatani. | 3.1 |  |  | 3.1 | Collector, Khurda Ltr. No. 21 dt-5-1-09 | C.W. | 3.1 | BBSR-II |  |  | 3.1 |  |  | 3.1
[7 empty] | E.I. | 0.41 | G.E.D.-I | 09-10 | 0.41 | 0 |  |  | 0
[7 empty] | P.H. | 0.47 | G.P.H.-I | 09-10 | 0.47 | 0 |  |  | 0
|  | 3.1 |  |  | 3.1 |  | Total = | 3.98 |  |  | 0.88 | 3.1 |  |  | 3.1
| Total (BBSR-II) = | 3.1 |  |  | 3.1 |  |  | 3.98 |  |  | 0.88 | 3.1 |  |  | 3.1
14 | Construction of Facilitation centre at Collectorate, Bolangir. |  |  | 1.41 | 1.41 | Dy. Collector (Nizarat), Bolangir Ltr. No. 515 dt-17-12-08 | C.W. | 3.12 | Bolangir | 08-09 | 2.5 |  |  | 0.62 | 0.62
[7 empty] | E.I. | 0.32 | G.E.D.-III |  |  |  |  | 0.32 | 0.32
[7 empty] | P.H. | 0.47 | G.P.H.-II |  |  |  |  | 0.47 | 0.47
|  |  |  | 1.41 | 1.41 |  | Total = | 3.91 |  |  | 2.5 |  |  | 1.41 | 1.41
15 | Construction of Facilitation centre at Sub-Collector office at Bolangir. |  |  | 1.41 | 1.41 | Dy. Collector (Nizarat), Bolangir Ltr. No. 515 dt-17-12-08 | C.W. | 3.12 | Bolangir | 08-09 | 2.5 |  |  | 0.62 | 0.62
[7 empty] | E.I. | 0.32 | G.E.D.-III |  |  |  |  | 0.32 | 0.32
[7 empty] | P.H. | 0.47 | G.P.H.-II |  |  |  |  | 0.47 | 0.47
|  |  |  | 1.41 | 1.41 |  | Total = | 3.91 |  |  | 2.5 |  |  | 1.41 | 1.41
16 | Construction of Facilitation centre at Tahasil office at Bolangir. |  |  | 1.41 | 1.41 | Dy. Collector (Nizarat), Bolangir Ltr. No. 515 dt-17-12-08 | C.W. | 3.12 | Bolangir | 08-09 | 2.5 |  |  | 0.62 | 0.62
[7 empty] | E.I. | 0.32 | G.E.D.-III |  |  |  |  | 0.32 | 0.32
[7 empty] | P.H. | 0.47 | G.P.H.-II |  |  |  |  | 0.47 | 0.47
|  |  |  | 1.41 | 1.41 |  | Total = | 3.91 |  |  | 2.5 |  |  | 1.41 | 1.41
17 | Construction of Facilitation centre at Collectorate, Subarnapur. |  |  | 1.45 | 1.45 | Collector, Sonepur Ltr. No. 8011 dt-12-9-08 | C.W. | 3.15 | Bolangir | 08-09 | 2.5 |  |  | 0.65 | 0.65
[7 empty] | E.I. | 0.32 | G.E.D.-III |  |  |  |  | 0.32 | 0.32
[7 empty] | P.H. | 0.48 | G.P.H.-II |  |  |  |  | 0.48 | 0.48
|  |  |  | 1.45 | 1.45 |  | Total = | 3.95 |  |  | 2.5 |  |  | 1.45 | 1.45
18 | Construction of Facilitation centre at Sub-Collector office at Sonepur. |  |  | 1.45 | 1.45 | Collector, Sonepur Ltr. No. 8011 dt-12-9-08 | C.W. | 3.15 | Bolangir | 08-09 | 2.5 |  |  | 0.65 | 0.65
[7 empty] | E.I. | 0.32 | G.E.D.-III |  |  |  |  | 0.32 | 0.32
[7 empty] | P.H. | 0.48 | G.P.H.-II |  |  |  |  | 0.48 | 0.48
|  |  |  | 1.45 | 1.45 |  | Total = | 3.95 |  |  | 2.5 |  |  | 1.45 | 1.45
19 | Construction of Facilitation centre at Tahasil office at Sonepur. |  |  | 1.45 | 1.45 | Collector, Sonepur Ltr. No. 8011 dt-12-9-08 | C.W. | 3.15 | Bolangir | 08-09 | 2.5 |  |  | 0.65 | 0.65
[7 empty] | E.I. | 0.32 | G.E.D.-III |  |  |  |  | 0.32 | 0.32
[7 empty] | P.H. | 0.48 | G.P.H.-II |  |  |  |  | 0.48 | 0.48
|  |  |  | 1.45 | 1.45 |  | Total = | 3.95 |  |  | 2.5 |  |  | 1.45 | 1.45
20 | Construction of Facilitation centre at Tahasil office at Binika. |  |  | 1.45 | 1.45 | Collector, Sonepur Ltr. No. 8011 dt-12-9-08 | C.W. | 3.15 | Bolangir | 08-09 | 2.5 |  |  | 0.65 | 0.65
[7 empty] | E.I. | 0.32 | G.E.D.-III |  |  |  |  | 0.32 | 0.32
[7 empty] | P.H. | 0.48 | G.P.H.-II |  |  |  |  | 0.48 | 0.48
|  |  |  | 1.45 | 1.45 |  | Total = | 3.95 |  |  | 2.5 |  |  | 1.45 | 1.45
21 | Construction of Facilitation centre at Sub-Collector office at Biramaharajpur. |  |  | 1.45 | 1.45 | Collector, Sonepur Ltr. No. 8011 dt-12-9-08 | C.W. | 3.15 | Bolangir | 08-09 | 2.5 |  |  | 0.65 | 0.65
[7 empty] | E.I. | 0.32 | G.E.D.-III |  |  |  |  | 0.32 | 0.32
[7 empty] | P.H. | 0.48 | G.P.H.-II |  |  |  |  | 0.48 | 0.48
|  |  |  | 1.45 | 1.45 |  | Total = | 3.95 |  |  | 2.5 |  |  | 1.45 | 1.45
| Total (Bolangir) = | 0 | 0 | 11.48 | 11.48 |  |  | 31.48 |  |  | 20 |  |  | 11.48 | 11.48
Total (FC 2nd Ph.) = |  | 19.14 | 0 | 11.48 | 30.62 |  |  | 83.27 |  |  | 52.79 | 19.14 | 0 | 11.48 | 30.62
Total (FC) = |  | 47.04 | 7.5 | 21.58 | 76.12 |  |  | 274.897 |  |  | 198.11 | 47.04 | 7.5 | 21.58 | 76.12
| Grand Total = | 291.14 | 73 | 110.48 | 474.62 |  |  | 3614.677 |  |  | 1063.83 | 248.7 | 62.87 | 108.78 | 420.35

## Health & F.W.-SP
Statement showing Allotment of funds for Building works of H & FW Department (SP) 2010-11
[8 empty] | Date :- 24-5-2010 | [6 empty] | (Rs. in Lakhs)
Sl. No. | Head of Account / Name of the Work | OBP of 2010-11 | 1st Supply. 2010-11 | Re-appro. 2010-11 | Surre. 2010-11 | Total | A.A. Cost with No. & Date |  |  | Name of Division | Funds alloted upto 3/2010 | Funds alloted 2010-11 | Expdr. till 2009-10 | Expdr. During 2010-11 | Physical Progress | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  |  | 9 | 10 | 11 | 12 | 13 | 14 | 15
D. No-7-4210-COL-on-M & P.H.-S.P.- S.S. - 01-UHS-110 -H & D -HEALTH & F.W. DEPARTMENT
1 | Constn. of Super Specialist Block of VSS Medical College & Hospital, Burla. | 89.44 |  |  |  | 89.44 | DMET No. 13668 dt.4.10.08 | C.W. | 69.74 | Baragarh | 75.85 |  | 97.26 |  | Work in progress | Finishing work in progress.
[8 empty] | E.I. | 6.97 | GED-III | 6.97
[8 empty] | P.H.(I) | 6.97 | GPH-II | 14.44
[8 empty] | P.H.(E) | 6.97
[8 empty] | Total = | 90.65 |  | 97.26 | 0 | 97.26 | 0
2 | Burn Unit of VSS Medical College & Hospital, Burla. (GF & FF) | 57.69 |  |  |  | 57.69 | DMET No. 7505 dt.10.6.06 | C.W. | 23.99 | Baragarh | 26 |  | 34.4 |  | Completed
[8 empty] | E.I. | 2.4 | GED-III | 2.4
[8 empty] | P.H.(I) | 2.4 | GPH-II | 6
[8 empty] | P.H.(E) | 3.6
[8 empty] | Total = | 32.39 |  | 34.4 | 0 | 34.4 | 0
| Burn Unit of VSS Medical College & Hospital, Burla. (SF & TF) | [5 empty] | DMET No. 13663 dt.4.10.08 | C.W. | 59.73 | Baragarh | 47 | 12.73 | 55.97 |  | Wok in progress | 2nd floor roof slab cast, 3rd floor roof slab to be casted. Finishing work in progress.
[8 empty] | E.I. | 5.97 | GED-III | 3 | 2.97
[8 empty] | P.H.(I) | 5.97 | GPH-II | 5.97 | 5.97
[8 empty] | P.H.(E) | 5.97
[8 empty] | Total = | 77.64 |  | 55.97 | 21.67 | 55.97 | 0
3 | Constn. of Orthopedic ward at VSS MCH, Burla. | 83.47 |  |  |  | 83.47 | DMET No.7550 / 16.06.06 | C.W. | 41.05 | Baragarh | 16.46 | 24.59 | 25.9 |  | Work in progress
[8 empty] | E.I. | 4.1 | GED-III | 0.18 | 3.92
[8 empty] | P.H.(I) | 4.1 | GPH-II | 9.26 | 1
[8 empty] | P.H.(E) | 6.16
[8 empty] | Total = | 55.41 |  | 25.9 | 29.51 | 25.9 | 0
| Constn. of Orthopedic ward at VSS MCH, Burla. |  |  |  |  | 0 | H & FW No.26820 / 3.12.08 | C.W. | 155.57 | Baragarh | 60 | 43.96 | 68.78 |  | Work in progress | Finishing work in progress.
[8 empty] | E.I. | 15.56 | GED-III |  | 5
[8 empty] | P.H.(I) | 15.56 | GPH-II | 8.78 | 5
[8 empty] | P.H.(E) | 15.56
[8 empty] | Total = | 202.25 |  | 68.78 | 53.96 | 68.78 | 0
4 | Constn. of 100 seated U.G. Hostel, VSS MCH, Burla. | 87.35 |  |  |  | 87.35 | DMET No. 48 dt. 2-1-09 | C.W. | 164.86 | Baragarh | 155 | 9.86 | 188 |  | Work in progress | Finishing work in progress.
[8 empty] | E.I. | 13.64 | GED-III | 8 | 5.64
[8 empty] | P.H.(I) | 13.54 | GPH-II | 25 | 8.85
[8 empty] | P.H.(E) | 20.31
[8 empty] | Total = | 212.35 |  | 188 | 24.35 | 188 | 0
5 | Constn. of Gate and Drainage System at VSS MCH, Burla. | 35 |  |  |  | 35 |  | C.W. |  | Baragarh | [5 empty] | NEW
[8 empty] | Total = | 0 |  | 0 | 0 | 0 | 0 |  | Estimate under preparation
Schedule Case Component Plan (SCCP)
6 | Infrastructure development as per MCI norms, VSS MCH, Burla. | 100 |  |  |  | 100 |  | C.W. |  | Baragarh | [5 empty] | NEW
[8 empty] | Total = | 0 |  | 0 | 0 | 0 | 0 |  | Principal to give the details scope of the work.
7 | Constn. of Skin & VD Dept. VSS MCH, Burla. | 40 |  |  |  | 40 |  | C.W. |  | Baragarh | [5 empty] | NEW
[8 empty] | Total = | 0 |  | 0 | 0 | 0 | 0 |  | CA addressed for supply of architectural drawing.
8 | Constn. attendant shed. VSS MCH, Burla. | 25 |  |  |  | 25 |  | C.W. |  | Baragarh | [5 empty] | NEW
[8 empty] | Total = | 0 |  | 0 | 0 | 0 | 0 |  | CA addressed for supply of architectural drawing.
Tribal Area Sub Plan (TASP)
9 | Constn. of super Specialist Block of VSS MCH, Burla (FF). | 40 |  |  |  | 40 | DMET No. 9003 dt. 16-6-10 | C.W. | 142.53 | Baragarh |  | 40 |  |  |  | NEW
[8 empty] | E.I. | 21.17 | G.E.D.-III | [5 empty] | Estimate submitted to DMET.
[8 empty] | P.H. | 14.11 | G.P.H.-II
[8 empty] | Total = | 177.81 |  | 0 | 40 | 0 | 0
10 | Constn. of Multi Utility complex VSS MCH, Burla (FF & SF) | 40 |  |  |  | 40 | DMET No. 9008 dt. 16-6-10 | C.W. | 42.35 | Baragarh |  | 40 |  |  |  | NEW
[8 empty] | E.I. | 6.28 | G.E.D.-III | [5 empty] | Estimate submitted to DMET.
[8 empty] | P.H. | 4.2 | G.P.H.-II
[8 empty] | Total = | 52.83 |  | 0 | 40 | 0 | 0
11 | Constn. of Modernisation lundry, VSS MCH, Burla. | 35 |  |  |  | 35 |  | C.W. |  | Baragarh | [5 empty] | NEW
[8 empty] | Total = | 0 |  | 0 | 0 | 0 | 0 |  | Estimate submitted to Principal, VSS, Burla.
12 | Constn. of Library, VSS MCH, Burla (FF). | 50 |  |  |  | 50 |  | C.W. | 40.6 | Baragarh |  | 40.6 |  |  |  | NEW
[8 empty] | E.I. | 6.03 | G.E.D.-III |  | 5.4 |  |  |  | Estimate submitted to DMET.
[8 empty] | P.H. | 4.02 | G.P.H.-II |  | 4
[8 empty] | Total = | 50.65 |  | 0 | 50 | 0 | 0
| Total (Bargarh) = | 682.95 | 0 | 0 | 0 | 682.95 |  |  | 717.34 |  | 401.53 | 259.49 | 367.13 | 0
13 | Constn. of Cardiology, SCB MCH, Cuttack. | 70 |  |  |  | 70 | H & FW No.17108 / 21.7.08 | C.W. | 351.86 | Cuttack | 351.86 |  |  |  | Work in progress | NEW
[8 empty] | E.I. (I) | 101.49 | GED-II | 88.5 | 17.99
[8 empty] | E.I. (E) | 10
[8 empty] | P.H.(E) | 27.59 |  | 27.26 | 8.83
[8 empty] | Total = | 490.94 |  | 467.62 | 26.82 | 0 | 0
[8 empty] | C.W. | [7 empty] | Estimate under preparation for new work.
[8 empty] | Total = | 0 |  | 0 | 0 | 0 | 0
14 | Constn. of Palmonory unit of SCB MCH, Cuttack. | 81.29 |  |  |  | 81.29 | DMET No6591 / 14.5.08 and No971 / 30.1.10 | C.W. | 109.06 | Cuttack | 95 | 14.06 |  |  | Work in progress | NEW
[8 empty] | E.I. (I) | 10.1 | GED-II | 10.1 | 5
[8 empty] | E.I. (E) | 5
[8 empty] | P.H.(I) | 10.1 | GPH-I | 24 | 1.25
[8 empty] | P.H.(E) | 15.15
[8 empty] | Total = | 149.41 |  | 129.1 | 20.31 | 0 | 0
[8 empty] | C.W. |  | Cuttack | [5 empty] | Estimate under preparation for new work.
[8 empty] | Total = | 0 |  | 0 | 0 | 0 | 0
15 | Constn. of Skin and VD of SCB MCH, Cuttack. | 49.2 |  |  |  | 49.2 | DMET No.14036 / 31.12.09 | C.W. | 39.92 | Cuttack | 40 |  | 68.5 |  | Work in progress | NEW
[8 empty] | E.I. (I) | 16.34 | GED-II | 13 | 13.34
[8 empty] | E.I. (E) | 10
[8 empty] | P.H.(I) | 7.44 | GPH-I | 15.5 | 2.44
[8 empty] | P.H.(E) | 10.5
[8 empty] | Total = | 84.2 |  | 68.5 | 15.78 | 68.5 | 0
[8 empty] | C.W. |  | Cuttack | [5 empty] | Estimate under preparation for new work.
[8 empty] | Total = | 0 |  | 0 | 0 | 0 | 0
16 | Trauma ward 2nd and 3rd floor building of SCB MCH, Cuttack | 102.87 |  |  |  | 102.87 | H & FW Dept. Lt No.26106 Dt.05.11.09 | C.W. | 151.98 | Cuttack | 15 | 87.87 | 36.5 |  | Work in progress. | NEW
[8 empty] | E.I. (I) | 51.97 | GED-II | 19 | 10 |  |  |  | Upto roof level.
[8 empty] | E.I. (E) | 3
[8 empty] | P.H.(I) | 9.92 | GPH-I | 2.5 | 5
[8 empty] | P.H.(E) | 6
[8 empty] | Total = | 222.87 |  | 36.5 | 102.87 | 36.5 | 0
17 | Constn. of Dental wing 2nd and 3rd floor of SCB MCH, Cuttack | 158.47 |  |  |  | 158.47 | H & F.W. Deptt. No. 29930 dt.07.10.09 | C.W. | 239.98 | Cuttack | 90 | 117.89 | 103 |  | Work in progress | Roof slab of 2nd and 3rd cast & filler walls completed & finishing work is in progress.
[8 empty] | E.I. (I) | 43.18 | GED-II | 5 | 30.18
[8 empty] | P.H.(I) | 8.1 | GPH-I | 8 | 10.4
[8 empty] | P.H.(E) | 17.3
[8 empty] | Total = | 308.56 |  | 103 | 158.47 | 103 | 0
18 | Constn. of Paediatric & Eye ward over the Eye ward of SCB MCH, Cuttack | 50 |  |  |  | 50 | H & FW Dept. Lt No.25217 Dt.27.10.09 | C.W. | 280.88 | Cuttack | 100 | 40 | 100 |  | Work in progress. | FF roof cast cmplete + 2nd floor column in roof level
[8 empty] | E.I. | 16.37 | GED-II |  | 5
[8 empty] | P.H.(I) | 12.55 | GPH-I |  | 5
[8 empty] | P.H.(E) | 41.72
[8 empty] | Total = | 351.52 |  | 100 | 50 | 100 | 0
19 | Constn. of new Medicine ward of SCB MCH, Cuttack | 44.81 |  |  |  | 44.81 | DME&T Orissa, No. 10838 dt.13.10.09 | C.W. | 100.23 | Cuttack | 25 | 39.81 | 50 |  | Work in progress. | NEW
[8 empty] | E.I. | 30.27 | GED-II | 20.58 | 3 |  |  |  | FF roof cast cmplete + 2nd floor column in roof level
[8 empty] | P.H. | 14.31 | GPH-I | 4.42 | 2
[8 empty] | Total = | 144.81 |  | 50 | 44.81 | 50 | 0
20 | Constn. of U.G. Hostel (100 seated for Boy's) at S.C.B. MCH, Cuttack. (1st and 2nd floor) | 66.17 |  |  |  | 66.17 | DMET Lt. No.10833 dt13.10.09 | C.W. | 101.79 | Cuttack | 67.72 | 34.07 | 86.19 |  | Work in progress. | 1st + 2nd floor roof cast complete. Finishing work in progress.
[8 empty] | E.I. (I) | 7.13 | G.E.D.-II | 7 | 5.13
[8 empty] | E.I. (E) | 5
[8 empty] | P.H. (I) | 10.1 | G.P.H.-I | 11.47 | 3.63
[8 empty] | P.H. (E) | 5
[8 empty] | Total = | 129.02 |  | 86.19 | 42.83 | 86.19 | 0
21 | Constn. of 3rd floor AHRCC, Cuttack | 108.44 |  |  |  | 108.44 | DMET No.9273 / 18.07.08 H&FW No.5145 / 28.2.09 | C.W. | 111.82 | Cuttack | 50 | 40 |  |  | Work in progress. | Tender in process for the Interior work of 3rd floor.
[8 empty] | E.I. | 90.04 | G.E.D.-II |  | 61.86
[8 empty] | P.H. | 6.58 | G.P.H.-I |  | 6.58
[8 empty] | Total = | 208.44 |  | 50 | 108.44 | 0 | 0
22 | Constn. of Paediatric, SVPPGI, Cuttack. | 8.8 |  |  |  | 8.8 | DMET No.11444 / 27.08.08 | C.W. | 30 | Cuttack | 20 | 8.8 |  |  | Completed | Account is to be squared up.
[8 empty] | E.I. |  | GED-I
[8 empty] | P.H. |  | GPHD-I | 1.2
[8 empty] | Total = | 30 |  | 21.2 | 8.8 | 0 | 0
23 | Infrastructure Development as per MCI norms in SCB MCH, Cuttack. | 50 |  |  |  | 50 |  | C.W. |  | Cuttack | [5 empty] | NEW
[8 empty] | Total = | 0 |  | 0 | 0 | 0 | 0 |  | Principal has been addressed to provide detail requiremnt vide E.E.s Lt. No.2791 dt.4.5.10
24 | EI installation of various Dept. including Surgical ICU, SCB MCH, Cuttack. | 50 |  |  |  | 50 | DMET No. 5407 dt- 25-5-10 | E.I. | 19.96 | G.E.D.-II |  | 19.96 |  |  |  | NEW
[8 empty] | Total = | 19.96 |  | 0 | 19.96 | 0 | 0 |  | Est. submitted
25 | Single OPD complex SCB MCH, Cuttack. | 50 |  |  |  | 50 |  | C.W. |  | Cuttack | [5 empty] | NEW
[8 empty] | Total = | 0 |  | 0 | 0 | 0 | 0 |  | CA has been addressed for drawing vide E.E.s Lt.2794 dt.4.5.10
26 | Impvt. to Micro-biology Dept. SCB MCH, Cuttack. | 50 |  |  |  | 50 |  | C.W. |  | Cuttack | [5 empty] | NEW
[8 empty] | Total = | 0 |  | 0 | 0 | 0 | 0 |  | CA has been addressed for drawing vide E.E.s Lt.2797 dt.4.5.10
27 | Annex bldg. Dental college, SCB MCH, Cuttack. | 50 |  |  |  | 50 |  | C.W. |  | Cuttack | [5 empty] | NEW
[8 empty] | Total = | 0 |  | 0 | 0 | 0 | 0 |  | CA has been addressed for drawing
28 | Constn. of X-ray block, SCB MCH, Cuttack. | 10 |  |  |  | 10 |  | C.W. |  | Cuttack | [5 empty] | NEW
[8 empty] | Total = | 0 |  | 0 | 0 | 0 | 0 |  | CA has been addressed for drawing vide E.E.s Lt.2827 dt.6.5.10
29 | Constn. of boundary wall, SCB MCH, Cuttack. | 50 |  |  |  | 50 |  | C.W. |  | Cuttack | [5 empty] | NEW
[8 empty] | Total = | 0 |  | 0 | 0 | 0 | 0 |  | Est. under preparation.
| Total (Cuttack) = | 1050.05 | 0 | 0 | 0 | 1050.05 |  |  | 1415.18 |  | 446.89 | 599.09 | 375.69 | 0
30 | Constn. of 216 seated U.G. hostel (SF) of MKCG MCH, Berhampur. | 101.55 |  |  |  | 101.55 | H & F.W. Deptt. No. 1670 dt. 29-1-09 | C.W. | 256.21 | Ganjam-I | 245.45 | 10.76 | 283.45 |  |  | NEW
[8 empty] | E.I. | 25.37 | GED-I | 20 | 5.37 |  |  |  | Est. amounting to Rs.126 lakh (SF) has already been submitted to the Principal MKCG vide E.E.s Lt.7458 dt.6.5.10 for AA
[8 empty] | P.H.(I) | 25.37 | GPH-I | 18 | 45.42
[8 empty] | P.H.(E) | 38.05
[8 empty] | Total = | 345 |  | 283.45 | 61.55 | 283.45 | 0
31 | Constn. of 2nd and 3rd floor of Paediatric Deptt. building of MKCG MCH, Berhampur. | 143.38 |  |  |  | 143.38 | DME&T Orissa, No. 10859 dt.13.10.09 | C.W. | 151.07 | Ganjam-I | 30 | 115.07 | 30 |  | work in progress | Work upto roof level
[8 empty] | E.I. | 32.87 | G.E.D.-I |  | 20.87
[8 empty] | P.H. | 9.44 | G.P.H.-I |  | 7.44
[8 empty] | Total | 193.38 |  | 30 | 143.38 | 30 | 0
32 | Constn. of SF and TF of Orthopedic Deptt. of MKCG MCH, Berhampur. | 102.6 |  |  |  | 102.6 | DME&T Orissa, No. 10854 dt.13.10.09 | C.W. | 111.5 | Ganjam-I | 50 | 61.5 | 50 |  | work in progress | Work upto roof level
[8 empty] | E.I. | 32.83 | G.E.D.-I |  | 32.83
[8 empty] | P.H. | 8.27 | G.P.H.-I |  | 8.27
[8 empty] | Total = | 152.6 |  | 50 | 102.6 | 50 | 0
33 | Constn. of SF & TF of Medicine Deptt. of MKCG MCH, Berhampur. | 73.87 |  |  |  | 73.87 | H & FW Dept. Lt. No.25840 Dt.04.11.09. | C.W. | 201.5 | Ganjam-I | 25 | 58.87 | 25 |  | Work in progress | Work upto roof level
[8 empty] | E.I. | 56.52 | G.E.D.-I |  | 10
[8 empty] | P.H. | 15.85 | G.P.H.-I |  | 5
[8 empty] | Total = | 273.87 |  | 25 | 73.87 | 25 | 0
34 | Constn. of boundary wall around campus of MKCG MCH, Berhampur. | 90 |  |  |  | 90 | DME&T Orissa, No. 10843 dt.13.10.09 | C.W. | 200 | Ganjam-I | 20 | 90 | 20 |  | work in progress | 0
35 | Constn. of Drainage system of MKCG MCH, Berhampur. | 1 |  |  |  | 1 | DME&T Orissa, No. 10849 dt.13.10.09 | C.W. | 197 | Ganjam-I | 50 | 1 | 50 |  | work in progress | 0
36 | Constn. of internal road of MKCG, MCH, Berhampur. | 50 |  |  |  | 50 |  | C.W. |  | Ganjam-I | [5 empty] | NEW
[8 empty] | Total = | 0 |  | 0 | 0 | 0 | 0 |  | Est. amounting to Rs.325 lakh has already been submitted to the Principal MKCG vide E.E.s Lt.7408 dt.3.5.10 for AA
37 | Constn. of 4 nos. lecture theater to conduct UG and PH practical halls to meet MCI norms at MKCG, MCH, Berhampur. | 72 |  |  |  | 72 |  | C.W. |  | Ganjam-I | [5 empty] | NEW
[8 empty] | Total = | 0 |  | 0 | 0 | 0 | 0 |  | CA has been requested to furnish the detail drawing vide E.E.s Lt No7392 dt.3.5.10
38 | Separate library bldg. at MKCG, MCH, Berhampur. | 50 |  |  |  | 50 |  | C.W. |  | Ganjam-I | [5 empty] | NEW
[8 empty] | Total = | 0 |  | 0 | 0 | 0 | 0 |  | CA has been requested to furnish the detail drawing vide E.E.s Lt No7396 dt.3.5.10
39 | Exten. to Micro-biology Dept. MKCG MCH, Berhampur. | 88 |  |  |  | 88 |  | C.W. |  | Ganjam-I | [5 empty] | NEW
[8 empty] | Total = | 0 |  | 0 | 0 | 0 | 0 |  | CA has been requested to furnish the detail drawing vide E.E.s Lt No7404 dt.3.5.10
| Total (Berhampur) = | 772.4 | 0 | 0 | 0 | 772.4 |  |  | 2326.7 |  | 846.9 | 472.4 | 846.9 | 0
40 | Constn. of buildings for Inspector of Ayurveda Sundargarh. | 5 |  |  |  | 5 | D.I.M.H., Orissa No. 694 dt-16-01-06 | C.W. | 9.6 | Sundargarh | 4.6 | 5 | 7 |  | Completed | Account is to be squared up.
[8 empty] | E.I. | 0.96 | GED-III | 0.96
[8 empty] | P.H. | 1.44 | GPH-II | 1.44
[8 empty] | Total = | 12 |  | 7 | 5 | 7 | 0
| Total (Sundargarh) = | 5 | 0 | 0 | 0 | 5 |  |  | 12 |  | 7 | 5 | 7 | 0
41 | Impvt. of Gents hostel of Dr. ACH MC & H, Bhubaneswar. | 39.63 |  |  |  | 39.63 | DIMH (O) No. 13494 / 25.11.08 | C.W. | 52.74 | BBSR-I | 52.74 |  | 63.3 |  | Completed | Account is to be squared up.
[8 empty] | E.I.(I) | 5.28 | GED-I | 5.28
[8 empty] | P.H.(I) | 5.28 | GPH-I | 5.28
P.H.(E)
[8 empty] | Total = | 63.3 |  | 63.3 | 0 | 63.3 | 0
42 | Impvt. of Hospital bldg. of Dr. ACH MCH, BBSR (Radiology Unit) | 10 |  |  |  | 10 | DIMH (O) No. 15512 / 26.11.08 | C.W. | 29.72 | BBSR-I | 29.72 |  | 35.66 |  | Completed | Account is to be squared up.
[8 empty] | E.I. | 2.97 | GED-I | 2.97
[8 empty] | P.H. | 2.97 | GPH-I | 2.97
[8 empty] | Total = | 35.66 |  | 35.66 | 0 | 35.66 | 0
43 | Constn. of Postmortem Center Capital Hospital, BBSR. | 47.96 |  |  |  | 47.96 | DHS(O) No.581 / 2.2.09 | CW | 40.14 | BBSR-II |  | 40.14 |  |  |  | Roof slab cast. Finishig work in progress. Work slowed down due to want of balance fund funds required as the find place in the current year budget.
[8 empty] | E.I. | 3.91 | GED-I |  | 3.91
[8 empty] | P.H. | 3.91 | GPH-I |  | 3.91
[8 empty] | Total = | 47.96 |  | 0 | 47.96 | 0 | 0
44 | Constn. of Cardiac Care Unit, Capital Hospital, BBSR. | 35.68 |  |  |  | 35.68 | DHS(O) No.286 / 17.1.09 | CW | 39.92 | BBSR-II | 12 | 27.92 |  |  |  | Roof slab cast. Celling plaster plinth protection work completed. Floooring work & other finishing work in progress.
[8 empty] | E.I. | 3.88 | GED-I |  | 3.88
[8 empty] | P.H. | 3.88 | GPH-I |  | 3.88
[8 empty] | Total = | 47.68 |  | 12 | 35.68 | 0 | 0
45 | Renov. of Micro-biology Lab. State Drug Testing Lab. BBSR. | 4.55 |  |  |  | 4.55 |  | CW |  | BBSR-I | [5 empty] | Estimate under preparation for new work.
46 | Renov. of Micro-biology Lab. State Drug Testing Lab. BBSR. | 8.38 |  |  |  | 8.38 | DDC(O) No.9790 / 23.10.09 | CW | 8.39 | BBSR-I | 8.39 |  | 8.39 |  |  | Account is to be squared up.
47 | Up-grad. of Micro-biology Lab. State Drug Testing Lab. BBSR. | 42.51 |  |  |  | 42.51 | DDC(O) No.9790 / 23.10.09 | CW | 42.52 | BBSR-IV | 42.52 |  | 42.52 |  | Completed | Account is to be squared up.
| Total (BBSR) = | 188.71 | 0 | 0 | 0 | 188.71 |  |  | 245.51 |  | 161.87 | 83.64 | 149.87 | 0
48 | Constn. of Homoeopathic College at Sambalpur | 23
| Total = | 2722.11 | 0 | 0 | 0 | 2699.11 |  |  | 4716.73 | 0 | 1864.19 | 1419.62 | 1746.59 | 0
D. No-7-4216- Housing Col on - S.P.
1 | Constn. of Multi storied bldg. for doctors SCB MCH, Cuttack. | 100 |  |  |  | 100 |  | CW |  | Cuttack | [5 empty] | New work
[8 empty] | EI |  | GED-II
[8 empty] | PH |  | GPH-I
[8 empty] | Total | 0 |  | 0 | 0 | 0 | 0
2 | Constn. of 2 nos. D-type Staff Qtrs. SDH, Nilagiri, Balasore. | 0.89 |  |  |  | 0.89 | DHS(O) No10292 / 12.12.06 and No10499 / 20.12.06 | CW | 11.86 | Balasore | 11.86 |  | 13.99 |  | Completed | Liability to be cleared
[8 empty] | EI | 1.24 | GED-II | 0.88
[8 empty] | PH | 1.78 | GPH-I | 1.25
[8 empty] | Total | 14.88 |  | 13.99 | 0 | 13.99 | 0
| Total (BBSR) = | 100.89 | 0 | 0 | 0 | 100.89 |  |  | 14.88 |  | 13.99 | 0 | 13.99 | 0
| Grand Total = | 2823 | 0 | 0 | 0 | 2800 |  |  | 4731.61 |  | 1878.18 | 1419.62 | 1760.58 | 0

## Tourism-5452-SP
STATE PLAN
Statement Showing the Building works for the year 2010-2011 Name of the Department :- Tourism
(Rs. In Lakhs)
Sl. No. | Name of the Work | O.B. P | 1st Suppl. | A.A. Cost | Name of the (R&B) Divison | Allotment up to 03/2010 | Allottment 2010-11 | Expdr. | Physical Progress | Remarks
(1) | (2) | (3) |  | (4) | (5) | (6) | (7) | (8) | (9) | (10)
1 | Constn. of Tourist Complex at Digapahandi | 40.23 | [7 empty] | NEW

## Culture-SP
STATE PLAN
Statement Showing the Building works for the year 2010-2011 Name of the Department :- Culture
(Rs. In Lakhs)
Sl. No. | Name of the Work | O.B. P | 1st Suppl. | A.A. Cost | Name of the (R&B) Divison | Allotment up to 03/2010 | Allottment 2010-11 | Expdr. | Physical Progress | Remarks
(1) | (2) | (3) |  | (4) | (5) | (6) | (7) | (8) | (9) | (10)
1 | Renovation of Bhanjakala Mandap at Bhubaneswar. | 6.5

## Works_4216
Statement showing Allotment of Funds for Building works of Works Department Plan for 2010-11
Rs. in Lakhs
Sl. No. | Head of Account, Name of the Work | B. P. 2010-11 | A.A.Cost With No. & Date |  |  | Name of (R&B) Division | Funds Allotted till 03/2010 |  | Funds alloted 2010-11 | Remarks
(1) | (2) | (3) | (4) |  |  | (5) | (6) |  | (7) | (8)
WORKS DEPARTMENT
D. No-7-4216-SP-COL ON HOUSING-01-GRB-106-GPA-SS :-
1 | Construction of 1no. 'B' type qtrs. at Satyanagar, Bhubaneswar. | 3.19 | CE(B) order No.6497 dt.15.02.10 | C.W | 30.26 | BBSR - IV | C.W | 27.58 | 2.67
|  |  |  | E.I | 2.55 | GED - I | E.I | 2.03 | 0.52
|  |  |  | P.H | 3.73 | GPHD - I | P.H | 3.74
|  |  |  | Total | 36.54 |  | Total | 33.35 | 3.19
2 | Construction of 8no. 'C' type qtrs. at Satyanagar, Bhubaneswar. | 1.63 | CE(B) order No.8502 dt.15.02.10 | C.W | 33.6 | BBSR - IV | C.W | 31.97 | 1.63
|  |  |  | E.I | 2.6 | GED - I | E.I | 2.6
|  |  |  | P.H | 3.9 | GPHD - I | P.H | 3.9
|  |  |  | Total | 40.1 |  | Total | 38.47 | 1.63
3 | Construction of 8no. 'D' type qtrs. at Satyanagar, Bhubaneswar. | 1 | CE(B) order No.346 dt.15.10.08 | C.W | 65.7 | BBSR - IV | C.W | 68.7
|  |  |  | E.I | 9.48 | GED - I | E.I | 5.47 | 1
|  |  |  | P.H | 13.8 | GPHD - I | P.H | 13.8
|  |  |  | Total | 88.98 |  | Total | 87.97 | 1
4 | Construction of 8no. 'E' type qtrs. at Cuttack. | 56.89 | CE(B) order No.392 dt.25.11.08 | C.W | 104.82 | Cuttack | C.W | 38 | 56.89
|  |  |  | E.I | 11.39 |  | E.I
|  |  |  | P.H | 15.59 |  | P.H
|  |  |  | Total | 131.8 |  | Total | 38 | 56.89
5 | Construction of Asst. Engineer qtrs. Of Beleswar (R&B) Sub-Division. | 1.45 | CE(B) order No.317 dt.30.12.09 | C.W | 9.52 | Balasore | C.W | 9 | 0.52
|  |  |  | E.I | 0.52 | GED - II | E.I | 0.5
|  |  |  | P.H | 1.42 | GPHD - I | P.H | 0.5 | 0.93
|  |  |  | Total | 11.46 |  | Total | 10 | 1.45
6 | Construction of double storied 'E' type qtrs. for the staff of Baragarh (R&B) Division. | 11.53 | CE(B) order No.234 dt.7.11.09 | C.W | 23.72 | Baragarh | C.W | 18 | 5.72
|  |  |  | E.I | 2.23 | GED - III | E.I | 1 | 1.23
|  |  |  | P.H | 5.58 | GPHD - II | P.H | 1 | 4.58
|  |  |  | Total | 31.53 |  | Total | 20 | 11.53
7 | Construction of 2nos. 'F' type qtrs. at Manmunda.. | 8.11 | CE(B) order No.284 dt.27.8.08 CE(B) order No.28 dt.25.01.10 | C.W | 6.61 | Phulbani | C.W | 1 | 5.61
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H | 2.5 | GPH - II | P.H |  | 2.5
|  |  |  | Total | 9.11 |  | Total | 1 | 8.11
8 | Improvement to E.I. work of PWD qtrs. of defferent field offices. | 7.85 |  | C.W |  |  | C.W
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
9 | Improvement to P.H. work of PWD qtrs. of defferent field offices. | 1.85 |  | C.W |  |  | C.W
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
10 | Construction of 'B' type dupled qtrs. of for S.E., Southern (R&B) Circle, Berhampur. | 10 |  | C.W |  | Ganjam - I | C.W |  |  | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
11 | Construction of 1no. 'C' type qtrs. for E.E. at Bhanjanagar. | 7 |  | C.W |  | Bhanjanagar | C.W |  |  | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
12 | Construction of 4no. 'E' type qtrs. for the staff of E.E. at Bhanjanagar. | 5 |  | C.W |  | Bhanjanagar | C.W |  |  | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
13 | Construction of 4no. 'F' type qtrs. for the staff of E.E. at Bhanjanagar. | 5 |  | C.W |  | Bhanjanagar | C.W |  |  | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
14 | Construction of 1no. 'D' type qtr. at Kabisuryanagar. | 3 |  | C.W |  | Bhanjanagar | C.W |  |  | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
15 | Construction of 1no. 'E' type qtr. at Kabisuryanagar. | 4 |  | C.W |  | Bhanjanagar | C.W |  |  | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
16 | Construction of 2no. 'E' type qtrs. at Soroda. | 5 |  | C.W |  | Koraput | C.W |  |  | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
17 | Construction of 1no. 'C' type qtr. for the E.E. (R&B) Division, Bolangir. | 1.6 | CE(B) order No.277 dt.15.7.10 | C.W | 24.86 | Bolangir | C.W |  | 1.6 | NEW
|  |  |  | E.I | 2.46 | GED - III | E.I
|  |  |  | P.H | 3.69 | GPH - II | P.H
|  |  |  | Total | 31.01 |  | Total |  | 1.6
18 | Construction of 2nos. 'E' type qtr. for the J.E. of Basudevpur (R&B) Sub-Division. | 5 |  | C.W |  | Bhadrak | C.W
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
| Total = | 139.1 | [6 empty] | 85.4
789-S.C.P. FOR SCHEDULE CASTE :-
1 | Construction of 8no. 'E' type qtrs. at Cuttack. | 36.91 | CE(B) order No.392 dt.25.11.08 | C.W | 104.82 | Cuttack | C.W |  | 9.93
|  |  |  | E.I | 11.39 | GED - II | E.I |  | 11.39
|  |  |  | P.H | 15.59 | GPHD - I | P.H |  | 15.59
|  |  |  | Total | 131.8 |  | Total | 0 | 36.91
| Total = | 36.91 | [6 empty] | 36.91
796-T.A.S.P.
1 | Construction of 2nos. 'F' type qtrs. at Boudh. | 5.7 | CE(B) order No.285 dt.27.8.08 | C.W | 7.26 | Plulbani | C.W | 3 | 4.26
|  |  |  | E.I | 0.72 | GED - IV | E.I |  | 0.72
|  |  |  | P.H | 0.72 | GPH - II | P.H |  | 0.72
|  |  |  | Total | 8.7 |  | Total | 3 | 5.7
2 | Construction of 1nos. 'D' type qtrs. at Khariar. | 5 | CE(B) order No.315 dt.31.7.10 | C.W | 7.96 | Khariar | C.W
|  |  |  | E.I | 0.8 |  | E.I
|  |  |  | P.H | 1.99 |  | P.H
|  |  |  | Total | 10.75 |  | Total
3 | Construction of 1nos. 'E' type qtrs. at Khariar. | 3 | CE(B) order No.314 dt.31.7.10 | C.W | 6.58 | Khariar | C.W
|  |  |  | E.I | 0.66 |  | E.I
|  |  |  | P.H | 1.64 |  | P.H
|  |  |  | Total | 8.88 |  | Total
4 | Construction of 1no. 'C' type qtrs. for the E.E. (R&B) Division, Bolangir. | 8.4 | CE(B) order No.277 dt.15.7.10 | C.W | 24.86 | Bolangir | C.W |  | 8.4 | NEW
|  |  |  | E.I | 2.46 | GED - III | E.I
|  |  |  | P.H | 3.69 | GPH - II | P.H
|  |  |  | Total | 31.01 |  | Total |  | 8.4
5 | Construction of 4nos. 'E' type qtrs. for the staff of P.W.D. at Bolangir. | 10 | CE(B) order No.278 dt.15.7.10 | C.W | 36.01 | Bolangir | C.W |  | 10 | NEW
|  |  |  | E.I | 3.61 | GED - III | E.I
|  |  |  | P.H | 5.41 | GPH - II | P.H
|  |  |  | Total | 45.03 |  | Total |  | 10
6 | Construction of 4nos. 'F' type qtrs. for the staff of P.W.D. at Bolangir. | 5 | CE(B) order No.279 dt.15.7.10 | C.W | 20.09 | Bolangir | C.W |  | 5 | NEW
|  |  |  | E.I | 1.99 | GED - III | E.I
|  |  |  | P.H | 2.98 | GPH - II | P.H
|  |  |  | Total | 25.06 |  | Total |  | 5
7 | Construction of 2nos. 'D' type qtrs. at Phulbani. | 10 |  | C.W |  | Plulbani | C.W |  |  | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
8 | Construction of 'D' type qtrs. at Boudh. | 4 |  | C.W |  | Plulbani | C.W |  |  | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
| Total = | 51.1 | [6 empty] | 29.1
| Grant Total = | 227.11 | [6 empty] | 151.41

## Works_4059
Statement showing Allotment of Funds for Building works of Works Department Plan for 2010-11
Rs. in Lakhs
Sl. No. | Head of Account, Name of the Work | B. P. 2010-11 | A.A.Cost With No. & Date |  |  | Name of (R&B) Division | Funds Allotted till 03/2010 |  | Funds alloted 2010-11 | Remarks
(1) | (2) | (3) | (4) |  |  | (5) | (6) |  | (7) | (8)
D. No-7-4059-Col on-PW-S.P.-S.S.-01-0B-051
WORKS DEPARTMENT
1 | Construction of "Construction Academy at Gopalpur", Cuttack. | 122.48 | Works Deptt. No.18444 dt.12.11.08 | C.W | 613.33 | Jagatsinghpur | C.W | 651 | 25
|  |  |  | E.I | 67.74 | GED - II | E.I | 13 | 54
|  |  |  | P.H | 19.5 | GPHD - I | P.H | 16 | 5
|  |  |  | Total | 700.57 |  | Total | 680 | 84
2 | Construction of office building for external Aided Project & Library building inside EIC (Civil) office campus. | 139.62 | Works Deptt. No.18656 dt.18.11.08 | C.W | 450.35 | BBSR - I | C.W | 325.174 | 125.176
|  |  |  | E.I | 93.96 | GED - I | E.I | 18 | 14.444
|  |  |  | P.H | 24.99 | GPHD - I | P.H
|  |  |  | Total | 569.3 |  | Total | 343.174 | 139.62
3 | Construction of office building of Basta (R&B) Sub-Division, Basta. | 6.71 | CE(B) order No.289 dt.9.12.09 | C.W | 10 | Balasore | C.W | 6.26 | 3.74
|  |  |  | E.I | 0.95 | GED - II | E.I | 0.45 | 0.5
|  |  |  | P.H | 2.47 | GPHD - I | P.H |  | 2.47
|  |  |  | Total | 13.42 |  | Total | 6.71 | 6.71
4 | Construction of Baragarh (R&B) Sub-Division at Barqagarh. | 11.6 | CE(B) order No.240 dt.9.11.09 | C.W | 16.49 | Baragarh | C.W | 10 | 6.49
|  |  |  | E.I | 1.46 | GED - III | E.I |  | 1.46
|  |  |  | P.H | 3.65 | GPHD - II | P.H |  | 3.65
|  |  |  | Total | 21.6 |  | Total | 10 | 11.6
5 | Construction of Chief Architect office building. | 5 |  | C.W |  | BBSR - I | C.W |  |  | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
6 | Construction of Sub-Division office at Badachana. | 5 | CE(B) order No.280 dt.15.7.10 | C.W | 17.78 | Charbaita | C.W |  | 5 | NEW
|  |  |  | E.I | 1.56 | GED - II | E.I
|  |  |  | P.H | 3.91 | GPH - I | P.H
|  |  |  | Total | 23.25 |  | Total |  | 5
7 | Improvement to P.W.D. Rest Shed at Satapada. | 8 |  | C.W |  | Puri | C.W |  |  | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
8 | Improvement to Jayanagar I.B. at Aul. | 5 |  | C.W |  | Kendrapara | C.W |  |  | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
9 | Improvement to Neulpur I.B. at Jaipur. | 5 |  | C.W |  | Panikoili | C.W |  |  | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
10 | Improvement to Parajanga I.B. at Dhenkanal. | 5 |  | C.W |  | Dhenkanal | C.W |  |  | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
11 | Improvement to Division Office Building at Bhanjanagar. | 4 |  | C.W |  | Bhanjanagar | C.W |  |  | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
12 | Construction of Division office Building at Belaguntha. | 3 |  | C.W |  | Bhanjanagar | C.W |  |  | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
13 | Construction of Section office Building at Badagada. | 3 |  | C.W |  | Bhanjanagar | C.W |  |  | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
14 | Improvement to Sub-Division office building at Kabisuryanagar. | 5 |  | C.W |  | Bhanjanagar | C.W |  |  | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
15 | Improvement to Sub-Division office Building at Bhanjangar. | 5 |  | C.W |  | Bhanjanagar | C.W |  |  | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
16 | Improvement of Division office at Bhadrak. | 3 |  | C.W |  | Bhadrak | C.W
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
17 | Installation of work for Secretariat work through Automation System. | 400 |  | C.W |  | BBSR - I | C.W |  |  | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
| Total = | 736.41 | [6 empty] | 246.93
789-S.C.P. FOR SCHEDULE CASTE :-
1 | Construction of office building for external Aided Project & Library building inside EIC (Civil) office campus. | 195.38 | Works Deptt. No.18654 dt.18.11.08 | C.W | 450.35 | BBSR - I | C.W | 325.174
|  |  |  | E.I | 93.96 | GED - I | E.I | 18 | 61.414
|  |  |  | P.H | 24.99 | GPHD - I | P.H |  | 24.99
|  |  |  | Total | 569.3 |  | Total | 343.174 | 86.404
| Total = | 195.38 | [6 empty] | 86.404
796-T.A.S.P. :-
1 | Construction of "Construction Academy at Gopalpur", Cuttack. | 266.1 | Works Deptt. No.18444 dt.12.11.08 | C.W | 613.33 | Jagatsinghpur | C.W | 651
|  |  |  | E.I | 67.74 | GED - II | E.I | 13
|  |  |  | P.H | 19.5 | GPHD - I | P.H | 16
|  |  |  | Total | 700.57 |  | Total | 680
2 | Improvement of Section office Building at Boudh. | 3 |  | C.W |  | Phulbani | C.W |  |  | NEW
|  |  |  | E.I |  |  | E.I
|  |  |  | P.H |  |  | P.H
|  |  |  | Total |  |  | Total
| Total = | 269.1
| Grant Total = | 1200.89 | [6 empty] | 333.334

## S & M.E.-4216-SP
STATE PLAN
Statement Showing the Building works for the year 2010-2011 Name of the Department :- School & Mass Education
(Rs. In Lakhs)
Sl. No. | Head of Account / Name of the Work | O.B. P | 1st Suppl. | A.A. Cost |  |  | Name of the (R&B) Divison | Allotment up to 03/2010 | Allottment 2010-11 | Expdr. | Physical Progress | Remarks
(1) | (2) | (3) |  | (4) |  |  | (5) | (6) | (7) | (8) | (9) | (10)
D. No.-7-4216-Col on-Housing - 01- GRB- 106- GPA-SP- SS - 796 - TASP - 2340 - Constn. of building for colleges for the year 2010-11.
1 | Constn. of staff qtrs. of B.Ed. College, Phulbani, Kandhamala. | 50 |  | S & ME memo No.7286 dt.30.4.10 | C.W. |  | Phulbani |  | 50 |  |  | NEW
E.I.
P.H.
[5 empty] | Total = | 264.542 |  |  | 50

## S & ME_SP_4202
Statement showing allotment of funds for the Building works of School & Mass Education Deptt. under State Plan for the year 2010-11.
(Rs. in Lakhs)
Head of Account | Sl. No. | Name of the Work | Budget Provision during 2010-11 | A.A. Cost with letter No. & Date |  |  | Funds allotted till March 2010 |  | Name of Division | Funds alloted during 2010-11 | Expdr. | Physical Progress
(1) | (2) | (3) | (4) | (5) |  |  | (6) |  | (7) | (8) | (9) | (10)
D. No.-7-4202-Col on-Education Sports Arts & Culture - SP - SS - 01- General Education 202 - Secondary Education-2340-Construction of buildings for Colleges for the year 2010-11. | 1 | Construction of Administrative / Institution Building of D.I.E.T., Kendrapara at Balia. | 47.14 | DTE & SCERT Lt. No.6506 Dt.21.12.06 | C.W. = | 59.53 | CW = | 44.04 | Kendrapara | 10
[5 empty] | E.I. (I) = | 5.795 | E.I. = | 2.11 | GED - II | 4.85
[5 empty] | E.I. (E) = | 1.16
[5 empty] | P.H.(I)= | 5.795 |  |  | GPH - I | 10
[5 empty] | P.H.(E)= | 8.69
[5 empty] | Total = | 80.97 |  | 46.15
| 2 | Construction of 50 seated Hostel Building of D.I.E.T., Kendrapara at Balia. |  | DTE & SCERT Lt. No.5026 Dt.25.09.07 | C.W.= | 83.94 | CW = | 47.36 | Kendrapara | 12.29
[5 empty] | E.I.= | 8.06 |  |  | GED - II | 5
[5 empty] | P.H. = | 20.14 | P.H. = | 6 | GPH - I | 5
[5 empty] | Total = | 112.14 |  | 53.36 |  | 47.14
| 3 | Construction of Administrative / Institution Building of D.I.E.T., at Jagatsinghpur. | 62.18 | DTE & SCERT Lt. No.6438 Dt.21.12.06 | C.W.= | 91.53 | CW = | 73.92 | Jagatsinghpur | 14.18
[5 empty] | App.Ro.= | 2.32
[5 empty] | E.I. (I) = | 8.94 | E.I. = | 4.17 | GED - II | 3
[5 empty] | E.I.(E) = | 0.17
[5 empty] | P.H.(I) | 8.94 | PH = | 8 | GPH - I | 5
[5 empty] | P.H.(E) | 13.41
[5 empty] | Total = | 125.31 |  | 86.09
| 4 | Construction of 50 seated Hostel Building of D.I.E.T. at Jagatsinghpur. |  | DTE & SCERT Lt. No.5014 Dt.25.09.07 | C.W.= | 80.12 | CW = | 37.25 | Jagatsinghpur | 30
[5 empty] | App.Ro.= | 2.32
[5 empty] | E.I. = | 8.06 |  |  | GED - II | 5
[5 empty] | P.H. = | 19.56 | PH = | 8 | GPH - I | 5
[5 empty] | Total = | 110.06 |  | 45.25 |  | 62.18
| 5 | Construction of Administrative / Institution Building of D.I.E.T. at Chhendipada. | 72 | DTE & SCERT Lt. No.6662 Dt.29.12.06 | C.W.= | 54.25 | CW = | 46.99 | Angul | 7.26
[5 empty] | E.I.(I) = | 4.14 | E.I. = | 3.32 | GED - II | 0.99
[5 empty] | E.I.(E) = | 0.17
[5 empty] | P.H.(I) = | 5.14 | PH = | 7.84 | GPH - II | 5.01
[5 empty] | P.H.(E) = | 7.71
[5 empty] | Total = | 71.41 |  | 58.15
| 6 | Construction of 50 seated Hostel Building of D.I.E.T. at Chhendipada. |  | DTE & SCERT Lt. No.5032 Dt.25.09.07 | C.W.= | 67.13 | CW = | 35.17 | Angul | 31.96
[5 empty] | E.I. = | 6.62 | E.I. = | 3.43 | GED - II | 3.19
[5 empty] | P.H. = | 16.11 | PH = | 8.16 | GPH - II | 7.95
[5 empty] | Total = | 89.86 |  | 46.76 |  | 56.36
| 7 | Construction of Administrative / Institution Building of D.I.E.T., Nayagarh at Rajsunakhala. | 57.64 | DTE & SCERT Lt. No.6657 Dt.29.12.06 | C.W.= | 52.6322 | CW = | 50.93 | Khurda | 1.7
[5 empty] | E.I. = | 5.2632 |  |  | GED - I | 5.26
[5 empty] | P.H.(I) = | 5.2632 | PH = | 5.55 | GPH - I | 5
[5 empty] | P.H.(E) = | 7.8948
[5 empty] | Total = | 71.0535 |  | 56.48
| 8 | Construction of 50 seated Hostel Building of D.I.E.T. at Rajsunakhala. |  | DTE & SCERT Lt. No.5047 Dt.25.09.07 | C.W.= | 56.73 | CW = | 25.4 | Khurda | 31.33
[5 empty] | E.I. = | 5.673 |  |  | GED - I | 5.67
[5 empty] | P.H. = | 14.1837 | PH = | 3.59 | GPH - I | 8.68
[5 empty] | Total = | 76.5867 |  | 28.99 |  | 57.64
| 9 | Construction of 30 seated Hostel building of D.R.C., Jharsuguda. | 18.55 | DTE & SCERT Lt. No.5413 Dt.15.10.07 | C.W.= | 39.53 | CW = | 27.1 | Sambalpur | 12.43
[5 empty] | E.I. = | 2.17 | E.I. = | 2.05 | GED - III | 0.12
[5 empty] | P.H.(E) = | 8.1 | PH = | 3 | GPH - II | 5.1
[5 empty] | Total = | 49.8 |  | 32.15 |  | 17.65
| 10 | Construction of 30 seated Hostel Building of D.R.C., Deogarh. | 18.3 | DTE & SCERT Lt. No.5483 Dt.16.10.07 | C.W.= | 37.74 | C.W.= | 12.6 | Sambalpur | 13
[5 empty] | E.I. = | 3.39 | E.I. = |  | GED - III | 2
[5 empty] | P.H. = | 8.47 | P.H. = |  | GPH - II | 3.3
[5 empty] | Total = | 49.6 | Total = | 12.6 |  | 18.3
| 11 | Construction of Administrative / Institution Building of Bhadrak at Agarpada. | 16.33 | DTE & SCERT Lt. No.4791 Dt.18.9.07 | C.W.= | 48.95 | C.W.= | 30 | Bhadrak | 12.33
[5 empty] | E.I. = | 5 | E.I. = |  | GED - II | 2
[5 empty] | P.H. = | 7.09 | P.H. = |  | GPH - I | 2
[5 empty] | Total = | 61.04 | Total = | 30 |  | 16.33
|  | Total = | 292.14 |  |  | 897.8302 |  | 495.98 |  | 275.6
D. No.-7-4202-Col on-Education Sports Arts & Culture SP - SS - 01- General Education 202 Secondary Education -SP- 796 - TASP for the year 2010-11 | 12 | Construction of Administrative / Institution Building of DRC, Malkangiri. | 17 | DTE & SCERT Lt. No.210 Dt.17.01.07 | C.W.= | 19.2726 | CW = | 10.08 | Malkangiri | 7.86
[5 empty] | E.I. = | 1.5617 | E.I. = |  | GED - IV | 1.56
[5 empty] | P.H. = | 1.5617 | PH = | 1.2 | GPH - II | 0.36
[5 empty] | Total = | 22.396 |  | 11.28
| 13 | Construction of 50 seated Hostel Building of D.I.E.T., Malkangiri. |  | DTE & SCERT Lt. No.5052 Dt.25.09.07 | C.W.= | 33.07 | CW = | 29 | Malkangiri | 4.07
[5 empty] | E.I. = | 3.265 | E.I. = | 2.19 | GED - IV | 1.08
[5 empty] | P.H. = | 3.265 | PH = | 1.2 | GPH - II | 2.07
[5 empty] | Total = | 39.6 |  | 32.39 |  | 17
| 14 | Construction of Administrative / Institution Building of D.R.C., Nuapada. | 12.65 | DTE & SCERT Lt. No.6668 Dt.29.12.06 | C.W.= | 10.04 | C.W.= | 10.04 | Khariar | -
[5 empty] | E.I. = | 0.985 | E.I. = | 0.98 | GED - IV | -
[5 empty] | P.H. = | 1.97 | P.H. = | 1.97 | GPH - II | -
[5 empty] | Total = | 12.995 | Total = | 12.99
| 15 | Construction of 30 seated Hostel Building of D.R.C., Nuapada. |  | DTE & SCERT Lt. No.6668 Dt.29.12.09 | C.W.= | 23.82 | C.W.= | 15.97 | Khariar | 7.85
[5 empty] | E.I. = | 2.34 | E.I. = |  | GED - IV | 2.34
[5 empty] | P.H. = | 5.84 | P.H. = | 5.84 | GPH - II | -
[5 empty] | Total = | 32 | Total = | 21.81 |  | 10.19
| 16 | Construction of Administrative Building of CT School at Phulbani. | 60 | DTE & SCERT Lt. No.4329 Dt.23.4.10 | C.W.= | 77.438 | C.W.= |  | Phulbani | 50 |  | NEW
[5 empty] | E.I. = | 7.562 | E.I. = |  | GED - IV | 5
[5 empty] | P.H. = | 7.563 | P.H. = |  | GPH - II | 5
[5 empty] | Total = | 92.563 | Total = | 0 |  | 60
| 17 | Construction of Hostel Building of CT School at Phulbani. | 60 | DTE & SCERT Lt. No.4329 Dt.23.4.10 | C.W.= | 83.82 | C.W.= |  | Phulbani | 50 |  | NEW
[5 empty] | E.I. = | 8.19 | E.I. = |  | GED - IV | 5
[5 empty] | P.H. = | 8.19 | P.H. = |  | GPH - II | 5
[5 empty] | Total = | 100.2 | Total = | 0 |  | 60
| 18 | Construction of Hostel Building of B.Ed. College at Phulbani (Kandhamal). | 180 | S & ME memo No.7277 dt.30.4.10 | C.W.= | 241.85 | C.W.= |  | Phulbani | 150 |  | NEW
[5 empty] | E.I. = | 20.11 | E.I. = |  | GED - IV | 12
[5 empty] | P.H. = | 30.16 | P.H. = |  | GPH - II | 18
[5 empty] | Total = | 292.12 | Total = | 0 |  | 180
| 19 | Construction of Administrative Building of B.Ed. College at Phulbani (Kandhamal). | 237 | S & ME No.7247 dt.30.4.10 | C.W.= |  | C.W.= |  | Phulbani | 217 |  | NEW
[5 empty] | E.I. = |  | E.I. = |  | GED - IV | 10
[5 empty] | P.H. = |  | P.H. = |  | GPH - II | 10
[5 empty] | Total = | 0 | Total = | 0 |  | 237
| 20 | Constn. of hostel Building of Sainik School at bhubaneswar | 113
| 21 | Constn. of building of 2nd Sainik School | 200 | [8 empty] | NEW
| 22 | Completion of Incomplete building at D.R.C., Sonepur. | 16.42
| 23 | Completion of Incomplete building at D.I.E.T., Balasore at Podasula (Nilagiri) | 41
| 24 | Completion of Incomplete Hostel building of T.E.& S.C.E.R.T. | 20.79
| 25 | Constn. of Administrative Building of C.T. School at Baliguda | 60 | [8 empty] | NEW
| 26 | Constn. of Hostel Building of C.T. School at Phulbani. | 40 | [8 empty] | NEW
|  | Total = | 1350 |  |  | 1489.7042 |  | 574.45 |  | 839.79

## H.E.-4202
STATE PLAN
Statement Showing the Building works for the year 2010-2011 Name of the Department :- Higher Education
(Rs. In Lakhs)
Sl. No. | Name of the Work | O.B. P | 1st Suppl. | A.A. Cost |  |  | Name of the (R&B) Divison | Allotment up to 03/2010 | Allottment 2010-11 | Expdr. | Physical Progress | Remarks
(1) | (2) | (3) |  | (4) |  |  | (5) | (6) | (7) | (8) | (9) | (10)
HIGHER DUCATION DEPARTMENT
4202 STATEPLAN
1 | Construction & completion of Rajadhani College, Bhubaneswar. | 125 |  | No. 10985 dt-10-2-98 | C.W. |  | Bhubaneswar-IV | 50 | 69.79 |  |  | Revised A.A. Rs. 221.66 lakhs submitted to Govt.
E.I.
P.H.
[5 empty] | Total = | 113.18 |  |  | 69.79
2 | Construction of Addl. Class Room of Bhadrak Jr. College. | 2 |  | No. 3361 dt-30-1-10 | C.W. | 20 | Bhadrak | 20
[5 empty] | E.I. | 2 | GED-II |  | 2
P.H.
[5 empty] | Total = | 22 |  |  | 2
3 | Constructin of Laboratory and Lecture Theatre of Bolangir Jr. Womens College. | 60.69 |  | No. 3138 dt-30-1-10 | C.W. | 100.57 | Bolangir |  | 54.69 |  | NEW
[5 empty] | E.I. | 10.06 | GED-III |  | 3
[5 empty] | P.H. | 10.06 | GPH-II |  | 3
[5 empty] | Total = | 120.69 |  |  | 60.69
4 | Construction of Lecture Theatre of FM College, Balasore. | 3.34 |  | No. 3366 dt-30-1-10 | C.W. | 19.478 | Balasore | 20 | 1.48
[5 empty] | E.I. | 1.93 | GED-II |  | 0.93
[5 empty] | P.H. | 1.93 | GPH-I |  | 0.93
[5 empty] | Total = | 23.338 |  |  | 3.34
5 | Construction of Lecture Theatre of N. C. College, Jajpur. | 5.27 |  | No. 3150 dt-30-1-10 | C.W. | 22.65 | Panikoili | 19.65 | 3
[5 empty] | E.I. | 2.27 | GED-II |  | 2.27
P.H.
[5 empty] | Total = | 24.92 |  |  | 5.27
HIGHER EDUCATION DEPARTMENT 796 TASP
1 | Construction of Womens Hostel at Phulbani. | 52.36 |  | No. 3142 dt-30-1-10 | C.W. | 49.89 | Phulbani | 10 | 39.89
[5 empty] | E.I. | 4.99 | GED-IV |  | 4.99
[5 empty] | P.H. | 7.48 | GPH-II |  | 7.48
[5 empty] | Total = | 62.36 |  |  | 52.36
2 | Construction of Laboratory and Lecture Theatre of Jeypore Jr. Womens College. | 32.37 |  | No. 3146 dt-30-1-10 | C.W. | 47.73 | Jeypore | 25 | 22.73
[5 empty] | E.I. | 4.77 | GED-IV |  | 4.77
[5 empty] | P.H. | 4.77 | GPH-II |  | 4.77
[5 empty] | Total = | 57.27 |  |  | 32.27
3 | Construction of Class Room of D.D. College, Keonjhar. | 18.99 |  | No. 2846 dt-28-1-10 | C.W. | 24.99 | Keonjhar | 7 | 17.99
[5 empty] | E.I. | 1 | GED-III |  | 1
P.H.
[5 empty] | Total = | 25.99 |  |  | 18.99
4 | Construction of Class Room of M.P.C. College, Baripada. | 9.65 |  | No. 3134 dt-30-1-10 | C.W. | 26.95 | Mayurbhanj | 20 | 6.95
[5 empty] | E.I. | 2.7 | GED-II |  | 2.7
P.H.
[5 empty] | Total = | 29.65 |  |  | 9.65
5 | Construction of 4 nos. class room of S.M. Govt. Women's College, Phulbani. | 68.97 |  | No. 40627 dt-4-10-08 | C.W. | 83.18 | Phulbani | 35 | 48.18
[5 empty] | E.I. | 8.32 | GED-IV |  | 8.32
[5 empty] | P.H. | 12.47 | GPH-II |  | 12.47
[5 empty] | Total = | 103.97 |  |  | 68.97
6 | Constn. Of Library-cum-reading room of S.M. Govt. Women's College, Phulbani. | 19.78 |  | No. 40635 dt-4-10-08 | C.W. | 28.32 | Phulbani | 15.62 | 13.32
[5 empty] | E.I. | 2.83 | GED-IV |  | 2.21
[5 empty] | P.H. | 4.25 | GPH-II |  | 4.25
[5 empty] | Total = | 35.4 |  |  | 19.78
| Total = | 398.42 | 0 |  |  | 618.768 |  | 222.27 | 343.11
NEW WORK
1 | New Block of Junior S.G. Women's College, Rourkela. | 80 | [9 empty] | NEW
2 | D.A.V. College, Koraput | 21.58 | [9 empty] | NEW
3 | Government Autonomous College, Bhawanipatana. | 20
4 | Foot over-bridge for Khallikote College, Berhampur. | 20 | [9 empty] | NEW
5 | Construction of work of Panchyat College, Baragarh | 60 | [9 empty] | NEW
| Total = | 201.58
| Grand Total = | 600 |  |  |  | 618.77 |  | 222.27 | 343.11

## GA-4059
Statement showing B.P. / Allotment of Funds for Building works of GA Department under State Plan for 2010-11
(Rs. in Lakhs)
Sl. No. | Name of the Work | Budget Estimate for 2010-11 | A.A. Cost with No. & Date |  | Name of Division | Funds Allotted till 03/2010 | Funds alloted during 2010-11 | Expdr. | Physical Progress | Remarks
(1) | (2) | (3) | (4) |  | (5) | (6) | (7) | (8) | (9) | (10)
D. No-7-4059 G.A. DEPARTMENT-State capital Projects
1 | Impvt. to Govt. Non-Res. building at Bhubaneswar & Cuttack (Lump) | 150 |  |  | BBSR-I
Cuttack
|  |  | Total = |  |  |  | 0
2 | Impvt. to Govt. Non-Res. building at Bhubaneswar & Cuttack Electrical installation work (Lump) | 150 |  |  | GED-I
GED-II
|  |  | Total = | 0 |  |  | 0
3 | Impvt. & S/R to Toshali Plaza - Civil works | 50 | [7 empty] | NEW
|  |  | Total = |  |  |  | 0
4 | Impvt. & S/R to Toshali Plaza - E.I. works | 0.01
5 | Impvt. Of Non-Residential Building of GAA, Bhubaneswar. | 20
| Total (D. No-7-4059-SP) = | 370.01 |  |  |  |  | 0

## GA-4216
Statement showing B.P. / Allotment of Funds for Building works of GA Department under State Plan for 2010-11
(Rs. in Lakhs)
Sl. No. | Name of the Work | Budget Estimate for 2010-11 | A.A. Cost with No. & Date | Name of Division | Funds Allotted till 03/2010 | Funds alloted during 2010-11 | Expdr. | Physical Progress | Remarks
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10)
D. No-7-4216-SP
1 | Impvt. to Govt. residential buildings at Bhubaneswar & Cuttack for Civil work (Lump) | 100 |  | Cuttack
BBSR-II
BBSR-III
BBSR-IV
|  |  |  | Total = |  | 0
2 | Impvt. to Govt. residential buildings at Bhubaneswar & Cuttack for Electrical installation work (Lump) | 165.4 |  | G.E.D.-I |  | 114.5
G.E.D.-II
|  |  |  | Total = |  | 114.5
3 | Relocation of G.A. Deptt. qtrs. at Cuttack. | 37 |  | Cuttack |  | 37
4 | Extension of Staircases to lower type flat qtrs. at Bhubaneswar. | 100 |  | BBSR-I |  | 11.55
|  |  |  | BBSR-II |  | -
|  |  |  | BBSR-III |  | 24.75
|  |  |  | BBSR-IV |  | 62.7
|  |  |  | Total = |  | 99
5 | Constn. of Garage to M.T. Flat qtrs. | 100 |  | BBSR-I
BBSR-II
BBSR-III
BBSR-IV
|  |  |  | Total = |  | 0
6 | Constn. of Garage to H.T. Flat qtrs. | 150 |  | BBSR-I
BBSR-II
BBSR-III
BBSR-IV
|  |  |  | Total = |  | 0
7 | Demolition of Bachelors barrack at Unit-VIII, Bhubaneswar. | 0.01 |  | BBSR-III
8 | Area development for residential / commercial / institutional purpose at Bhubaneswar. | 0.01
9 | Provision of common boundary wall / barbed wire fencing to residential qtrs. / blocks in different locations / areas units in Bhubaneswar. | 100 |  | BBSR-I
BBSR-II
BBSR-III
BBSR-IV
|  |  |  | Total = |  | 0
| Total (D. No-7-4216-SP) = | 752.42 |  |  |  | 250.5

## G.A. (Vig.)_4059_SP
Statement showing B.P. / Allotment of Funds for Non-Residential Building works of GA (Vig.) Department under State Plan for 2010-11
(Rs. in Lakhs)
Sl. No. | Head of Account / Name of the Work | Budget Provision 2010-11 |  | A.A. Cost with No. & Date |  |  | Name of Division | Funds Allotted till 03/2010 |  | Funds alloted 2010-11 |  | Expdr. | Physical Progress | Remarks
|  | O.B.P. | 1st Suppl. | [6 empty] | O.B.P. | 1st Suppl.
(1) | (2) | (3) |  | (4) |  |  | (5) | (6) |  | (7) |  | (8) | (9) | (10)
D. No-7-4059-SP
1 | Construction of Vigilance Unit office at Nayagarh. | 5.89 |  | No-5498 dt-28-07-09 | C.W. | 30.29 | Khurda | 09-10 | 30.29
[5 empty] | E.I. | 3.03 | G.E.D.-I | 09-10 | 1.5 | 1.53
[5 empty] | P.H. | 7.57 | G.P.H.-I | 09-10 | 3.21 | 4.36
[5 empty] | Total = | 40.89 |  |  | 35 | 5.89
2 | Construction of Vigilance Unit office at Jajpur. | 2.31 |  | No-6073 dt-19-08-09 (A.A. accorded for Rs. 37.31 lakhs) | C.W. | 29.38 | Panikoili | 09-10 | 27.88
[5 empty] | E.I. | 2.76 | G.E.D.-II | 09-10 | 0.5 | 1.31
[5 empty] | P.H. | 5.31 | G.P.H.-I | 09-10 | 2.36 | 1
[5 empty] | Total = | 37.45 |  |  | 30.74 | 2.31
3 | Construction of Vigilance Unit office at Kendrapara. | 9.08 |  | No-6250 dt-22-08-09 | C.W. | 32.47 | Kendrapara |  | 28.87 | 3.6
[5 empty] | E.I. | 5.48 | G.E.D.-II |  | 2.74 | 2.74
[5 empty] | P.H. | 5.484 | G.P.H.-I |  | 2.74 | 2.74
[5 empty] | Total = | 43.434 |  |  | 34.35 | 9.08
4 | Construction of Vigilance Unit office at Jagatsinghpur. | 8.39 |  | No-5544 dt-29-07-09 | C.W. | 35.665 | Jagatsinghpur | 09-10 | 23.73 | 8.39
[5 empty] | E.I. | 3.09 | G.E.D.-II | 09-10 | 0.5
[5 empty] | P.H. | 4.64 | G.P.H.-I | 09-10 | 1
[5 empty] | Total = | 43.395 |  |  | 25.23 | 8.39
5 | Renovation of S.P. Vigilance, Bhubaneswar Division office Building at Bhubaneswar. | 5.33 |  | No- 5644 dt. 30-6-10 | C.W. |  | BBSR-II |  |  | 5.33
E.I.
P.H.
[5 empty] | Total = | 0 |  |  | 0 | 5.33 | 0
Grand Total (D. No-7-4059-SP) = |  | 31 | 0 |  |  | 165.169 |  |  | 125.32 | 31 | 0

## P&C_4059
Statement showing B.P. / Allotment of Funds for Non-Residential Building works of P & C Department under State Plan for 2010-11
(Rs. in Lakhs)
Sl. No. | Head of Account / Name of the Work | Budget Provision for 2010-11 |  | A.A. Cost with No. & Date |  |  | Name of Division | Funds Allotted till 03/2010 |  | Funds alloted 2010-11 | Expdr. | Physical Progress | Remarks
|  | OBP | 1st Suppl.
(1) | (2) | (3) |  | (4) |  |  | (5) | (6) |  | (7) | (8) | (9) | (10)
D. No-7-4059 P&C DEPTT.
1 | Construction of compound wall for office building of Dy. Director (Statistics) Central Range, Cuttack & District Statistical Officer, Cuttack (South & West) side. | 10 |  | 4.98 No-3965 Dt. 01-5-10 of Director of Economics & Statistics | CW | 4.9815 | Cuttack |  |  | 4.9815 |  | 0 | NEW
E.I
P.H
[5 empty] | Total | 4.9815 |  |  | 0 | 4.9815 | 0 | 0
2 | Constn. of compound wall for office buildings of Dy. Director (Statistics) Central Range, Cuttack & District Statistical officer, Cuttack (North & East) side. |  |  | 4.98.00 No-3971 Dt. 01-5-10 of Director of Economics & Statistics | CW | 4.9815 | Cuttack |  |  | 4.9815 |  | 0 | NEW
E.I
P.H
[5 empty] | Total | 4.9815 |  |  | 0 | 4.9815 | 0 | 0
3 | Constn. of Office Building of different District Planning Offices | 90 | [10 empty] | NEW
4 | Constn. of compound wall for office buildings of Dy. Director (Statistics) Central Range, Cuttack & District Statistical officer, Cuttack. | 100 | [10 empty] | NEW
| Total = | 200 | 0 |  |  | 9.963 |  |  | 0 | 9.963 | 0 | 0

## P&C_4216
Statement showing B.P. / Allotment of Funds for Non-Residential Building works of P & C Department under State Plan for 2010-11
(Rs. in Lakhs)
Sl. No. | Head of Account / Name of the Work | Budget Provision for 2010-11 |  | A.A. Cost with No. & Date |  |  | Name of Division | Funds Allotted till 03/2010 |  | Funds alloted 2010-11 | Expdr. | Physical Progress | Remarks
|  | OBP | 1st Suppl.
(1) | (2) | (3) |  | (4) |  |  | (5) | (6) |  | (7) | (8) | (9) | (10)
D. No-7-4216 P&C DEPARTMENT
1 | Construction of Residential Building of District Planning Offices of Baragarh. | 38.21 |  | Letter No. 1125 dt-29-1-09 of P&C Deptt. | C.W. | 43.09 | Baragarh | 09-10 | 15 | 28.09
[5 empty] | E.I | 2.89 | GED.-III |  |  | 2.89
[5 empty] | P.H | 7.23 | GPH-II |  |  | 7.23
[5 empty] | Total | 53.21 |  |  | 15 | 38.21 | 0 | 0 | 0
2 | Constn. of staff qtrs. for the staff of different district Planning Offices (Lump) | 61.79 | [10 empty] | NEW
| G. Total = | 100

## L&E-4059
Statement showing B.P. / Allotment of Funds for Building works of L & E Department under State Plan for 2010-11
(Rs. in Lakhs)
Sl. No. | Head of Account / Name of the Work | Budget Provision for 2010-11 |  | A.A. Cost with No. & Date |  |  | Name of Division | Funds Allotted till 03/2010 |  | Funds alloted 2010-11 | Expdr. | Physical Progress | Remarks
|  | O.B.P. | 1st Suppl.
(1) | (2) | (3) |  | (4) |  |  | (5) | (6) |  | (7) | (8) | (9) | (10)
D. No-7-4059-796-TASP
1 | Constn. of Departmental office building of employment exchange office, Sundargarh. | 3.11 |  | Director Employment No- 3924 dt- 4-6-08 | C.W. | 25.54 | Sundargarh | 08-09 | 5.54 |  |  |  | NEW
[7 empty] | Sundargarh | 09-10 | 16.89
[5 empty] | E.I. | 2.23 | G.E.D.-III | 09-10 | 2.23
[5 empty] | P.H. | 2.23 | G.P.H.-II | 09-10 | 2.23
[5 empty] | Total | 30 |  |  | 26.89 | 0 | 0
2 | Construction of Department Office Building of D.E. Ex., Balasore (TASP). | 5.46 | [10 empty] | NEW
3 | Construction of Department Office Building of D.E. Ex., Cuttack. | 4 | [10 empty] | NEW
4 | Construction of Department Office Building of D.E. Ex., Keonjhar (TASP). | 21.96 | [10 empty] | NEW
5 | Construction of Department Office Building of D.E. Ex., Baragarh. | 4 | [10 empty] | NEW
6 | Construction of Department Office Building of D.E. Ex., Bhadrak (SCP). | 4 | [10 empty] | NEW
7 | Construction of Department Office Building of D.E. Ex., Jagatsinghpur (SCP). | 4.5 | [10 empty] | NEW
8 | Construction of Department Office Building of D.E. Ex., Jajpur (SCP). | 4.5 | [10 empty] | NEW
9 | Repair work with interior furnishing for Computer Room for 18 nos. of Employment Exchanges | 36 | [10 empty] | NEW
| Total (4059-SP) = | 87.53 | 0 |  |  | 30 |  |  | 26.89 | 0

## L&E-4216
Statement showing B.P. / Allotment of Funds for Building works of L & E Department under State Plan for 2010-11
(Rs. in Lakhs)
Sl. No. | Head of Account / Name of the Work | Budget Estimate for 2010-11 | A.A. Cost with No. & Date |  |  | Name of Division | Funds Allotted till 03/2010 |  | Funds alloted 2010-11 | Expdr. | Physical Progress | Remarks
(1) | (2) | (3) | (4) |  |  | (5) | (6) |  | (7) | (8) | (9) | (10)
D. No-7-4216-SP-District Sector -789-SCP for SC
1 | Construction of Residential staff qtrs. for the office of A.L.C. at Angul (SCP for SC). | 23 |  | C.W. | [7 empty] | NEW
E.I.
P.H.
| Total (4216-D.S.) = | 23 |  |  | 43 |  |  | 0 | 0 | 0 | 0

## I & P.R._4059
Statement showing B.P. / Allotment of Funds for Building works of I & P.R. Department under State Plan for 2010-11
(Rs. in Lakhs)
Sl. No. | Head of Account / Name of the Work | Budget Estimate for 2010-11 | A.A. Cost with No. & Date | Name of Division | Funds Allotted till 03/2010 | Funds alloted 2010-11 | Expdr. | Physical Progress | Remarks
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10)
1 | Construction of Office Building of DIPRO, Boudh | 4.65
2 | Impvt. Of Pavillion of Pragati Maidan, New Delhi | 5 |  | BBSR-II |  | 5
3 | Electrical maintenance of Pavillion of Pragati Maidan, New Delhi | 3
4 | Electrical renovation of Department Buuilding at Bhubaneswar. | 8
| Total = | 20.65 |  |  |  | 5

## Law Deptt _4216
Statement showing Allotment of Funds for Building works of Law Department (State Plan) for 2010-11
(Rs.in Lakhs)
Sl. No. | Head of Account, Name of the Work | B. P. 2010-11 | A.A.Cost With No. & Date |  |  | Name of Division | Funds Allotted till 03/2010 | Funds Allotted during 2010-11 (Incl.P.C) | Expenditure incurred | Physical Progress
(1) | (2) | (3) | (4) |  |  | (5) | (6) |  | (9) | (10)
D No.7-4059-Col on -P.W-S.P-01-OB-051-Constn.
1 | Improvement of office Building of Orissa Human Right Commission at Bhubaneswar. | 44.17 |  |  |  | BBSR - I
D.No.4216-Col on housing-S.P-01-GRB-106-GPA-796-TASP
2 | Construction of Staff Qrs.for the Staff of Civil Court, Jeypore | 8.53 | Rs.242.61 Law Deptt. L No.4551 dt-14.03.01 | C.W | 199.38 | Jeypore | 57.29 | 6.53 |  | 8 Nos. E-type & 8 Nos. F-type Completed in all respect. 4nos. E type quarters in progress.
|  |  |  | E.I | 17.29 | GED -IV | 3.59 | 1
|  |  |  | P.H | 25.94 | GPHD -II | 6.03 | 1
|  |  |  | Total | 242.61 |  | 66.91 | 8.53
D.No.4216-Col on housing-S.P-01-GRB-106-GPA
4 | Construction of Staff Qrs.for the Staff of Dist. Judge at Keonjhar. | 16.47 | Rev. A/A Rs.88.74 of Law Deptt. L.No.14018 dt-31.10.02 | C.W | 65.48 | Keonjhar | 51.05 | 14.37 |  | 1 No. D-type, 5Nos. E-type Completed. 4 Nos. F-type quarter in progress.
|  |  |  | E.I | 5.81 | GED -III | 1.51 | 1
|  |  |  | P.H | 17.45 | GPHD -II | 3.85 | 1.1
[5 empty] | 88.74 |  | 56.41 | 16.47
| Total | 25 |  | Total | 331.35 |  |  | 25

## Law_4059
Statement showing B.P. / Allotment of Funds for Building works of Law Department under State Plan for 2010-11
(Rs. in Lakhs)
Sl. No. | Head of Account / Name of the Work | Budget Estimate for 2010-11 | A.A. Cost with No. & Date | Name of Division | Funds Allotted till 03/2010 | Funds alloted 2010-11 | Expdr. | Physical Progress | Remarks
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10)
1 | Improvement of office Building of Orissa Human Right Commission at Bhubaneswar. | 44.17 | [6 empty] | NEW

## Sports_4202
Statement showing B.P. / Allotment of Funds for Building works of Sports Department under State Plan for 2010-11
(Rs. in Lakhs)
Sl. No. | Head of Account / Name of the Work | Budget Estimate for 2010-11 | A.A. Cost with No. & Date | Name of Division | Funds Allotted till 03/2010 | Funds alloted 2010-11 | Expdr. | Physical Progress | Remarks
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10)
1 | Construction of District Sports Complex at Puri, Khurda etc. | 48
2 | Construction of District Sports Complex at Kusadunguri (Kalahandi Dist.), Jajpur and other District. | 44
3 | Construction of District Sports Complex at Sundargarh, Koraput etc. and other Tribal District. | 36
| Total = | 128